## Pcodes for MCMB inouts
MOM: WARD SABHA: WARD 60 4June 2016
MINUTES OF MEETING- WARD 60 ; 4 June 2016 : Pcodes matching inputs received on MyCityMyBudget
Request Id | source Id | RWA Name | Request Title | Category | Request Description | User Name | Email Id | Category Name | Location | Ward No | Ward Name | Agency | AC | PC | Vote Up Count | Creadted Date | Budget Head | Budget Category | Budget Sub-category | Key1 | Key2 | Match in budget Key1? | Match in budget Key2? | Count of Data in MCMB | PCode | Pcode Description | Head | Category | Sub-Category | Level | Level Detail | Ward Name | Ward Number | Current Works | Spillover Works | Pending Bills | Unassigned Works | Total amt (current works+ pending bills+ unassigned work | MCMB Category | MCMB Sub-Category | Ward No. | Additional points raised by residents | Action points | responsibility | Timelines
Ward 60: Budget Category: Health Care Buildings
4901 | 5000 | Richards Town RWA | Require new Primary health centre/ community health centre | Require new Primary health centre/ community health centre | We do not have health centre in this area | Clarie Pinto | clariejohn@yahoo.com | Public health | Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:38:11 | Community Infrastructure | Health Care Buildings |  | Community Infrastructure-Health Care Buildings- | Community Infrastructure-Health Care Buildings | #REF! | #REF! | #REF! | P0979 | M & R of Hospitals, Maternity Homes, Dispensary & Doctors Qtrs / Clinical Laboratories | Community Infrastructure | Health Care Buildings |  |  |  | Sagayarapuram | 60 | 192307.6923 | 76923.0769 | 197865.3846 | 0 | 467096.1538 | Public health | Improve facilities in the existing Primary health centre/ community health centre | 60 | Not discussed | NA | NA | NA
[11 empty] | 0 |  | 0 | [11 empty] | P2168 | Upgradation of 29 Health Centers | Community Infrastructure | Health Care Buildings |  |  |  | Sagayarapuram | 60 | 0 | 0 | 0 | 0 | 0 | Public health | Improve facilities in the existing Primary health centre/ community health centre | 60
Ward 60 : Budget Category: Markets
3816 | 5000 | Richards Town RWA | Repair of government managed public markets | Repair of government managed public markets | This needs to be shifted out Place of low hygiene / bad smell Requires live stock to be brought here Animal waste is dumped all over The entire area stinks | Deepak Pinto | dpinto@zenithprecision.in | Public Utilities and services | Pottery road / Tannery road junction | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 13:45:06 | Community Infrastructure | Markets |  | Community Infrastructure-Markets- | Community Infrastructure-Markets | #REF! | #REF! | #REF! | P0462 | M & R of BBMP Markets Buildings | Community Infrastructure | Markets |  |  |  | Sagayarapuram | 60 | 212765.9574 | 89361.7021 | 230808.5106 | 212765.9574 | 745702.1277 | Public Utilities and services | Repair of government managed public markets | 60 | Not discussed | NA | NA | NA
3823 | 5000 | Richards Town RWA | Repair of government managed public markets | Repair of government managed public markets | Needs maintenance and proper efflment treatment | K.g.shashidhar | kg.shashidhar@gmail.com | Public Utilities and services | pottery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:03:15 | Community Infrastructure | Markets |  | Community Infrastructure-Markets- | Community Infrastructure-Markets | #REF! | #REF! | #REF! | P2181 | Construction of New Markets & Development of Old Markets under PPP Model | Community Infrastructure | Markets |  |  |  | Sagayarapuram | 60 | 0 | 0 | 16510.6383 | 0 | 16510.6383 | Public Utilities and services | Repair of government managed public markets | 60
4895 | 5000 | Richards Town RWA | Repair of government managed public markets | Repair of government managed public markets | Bad smell in our area very dirty bad hygiene | Snehalatha Naidu | snehaism@gmail.com | Public Utilities and services | pottery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:26:47 | Community Infrastructure | Markets |  | Community Infrastructure-Markets- | Community Infrastructure-Markets | #REF! | #REF! | #REF! | [16 empty] | 60
4897 | 5000 | Richards Town RWA | Repair of government managed public markets | Repair of government managed public markets | Abbation bad smell from this place very bad hygiene | Clarie Pinto | clariejohn@yahoo.com | Public Utilities and services | Tannery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:30:15 | Community Infrastructure | Markets |  | Community Infrastructure-Markets- | Community Infrastructure-Markets | #REF! | #REF! | #REF! | [16 empty] | 60
4913 | 5000 | Richards Town RWA | Repair of government managed public markets | Repair of government managed public markets | Very bad smell / very dirty area must be moved outside the city limits | Ahmed ali | Ahmed ali_rwauser@mailinator.com | Public Utilities and services | pottery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:09:37 | Community Infrastructure | Markets |  | Community Infrastructure-Markets- | Community Infrastructure-Markets | #REF! | #REF! | #REF! | [16 empty] | 60
4883 | 5003 | Richards Town RWA | Repair of government managed public markets | Repair of government managed public markets | Pottery road needs maintenance of buildings, proper treatment, water lighting etc | K G Shashidhar | Richards_T_98@ichangemycity.com | Public Utilities and services | Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:56:54 | Community Infrastructure | Markets |  | Community Infrastructure-Markets- | Community Infrastructure-Markets | #REF! | #REF! | #REF! | [16 empty] | 60
Ward 60: Budget Category: Road Related Works
3764 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Very big potholes which cause a traffic hazard | sunita | sunita.vaznaik@hotmail.com | Mobility - Roads, Public transport | Hall road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:17:40 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | P1771 | Zone Works - POW Works (Ward wise maintenance per Ward Rs.10 lakhs) | Mobility | Road Related Works | Asphalting and tarring works |  |  | Sagayarapuram | 60 | 11742424.2424 | 1893939.3939 | 2272727.2727 | 0 | 15909090.9091 | Mobility - Roads, Public transport | Construction of flyovers/ underpass | 60 | Based on the requirement of ensuring quality of work to be monitored proactively, it was suggested to the BBMP AE – Mr Krishnamurthy to put up the details of a tender once it has been approved. A start date and an end date for every work to be shared by the AE, so that we have closure dates before the next meeting. | Nagarothana grant will cover these issues and work will be started in 2-3 weeks | AE - Krishnamurthy | By 30th June
3794 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Several roads such as John Armstrong , Davis road etc needs tarring. | Suresh Varghese | varghesesuresh@yahoo.com | Mobility - Roads, Public transport | Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:34:39 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | P2187 | Development of approach roads to international Airport Road | Mobility | Road Related Works | Asphalting and tarring works |  |  | Sagayarapuram | 60 | 0 | 0 | 0 | 0 | 0 | Mobility - Roads, Public transport | Construction of flyovers/ underpass | 60
3797 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Sheelu Thomas | thomas_sheelu@yahoo.com | Mobility - Roads, Public transport | Richards town - John Armstrong road, Hall road, Davis road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:40:42 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | P3075 | Special Comprehensive Development Works in Bangalore city (Bangalore city incharge Minister's Discretionary Grants) | Mobility | Road Related Works | Asphalting and tarring works |  |  | Sagayarapuram | 60 | 6313131.3131 | 13333.3333 | 87401.5152 | 0 | 6413866.1616 | Mobility - Roads, Public transport | Construction of flyovers/ underpass | 60
3802 | 5000 | Richards Town RWA |  | Tarring of mud/unpaved roads | Tarring of mud/unpaved roads | Shubha Shetty | Shubha Shetty_rwauser@mailinator.com | Mobility - Roads, Public transport | Rogers road, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:49:31 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | P3128 | Construction of shelter to open area in Kurubarahalli Pipeline | Mobility | Road Related Works | Asphalting and tarring works |  |  | Sagayarapuram | 60 | 17676.7677 | 0 | 0 | 0 | 17676.7677 | Mobility - Roads, Public transport | Construction of flyovers/ underpass | 60
3809 | 5000 | Richards Town RWA |  | Tarring of mud/unpaved roads | Hall road extension to starting of hall road opposite to BESCOM office (All roads in Richards town has to be laid which are in dilapidated condition) | E T Ponnukuttan | chandkuttan1934@dataone.com | Mobility - Roads, Public transport | Hall road, Richards town, Bangalore-5 | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 12:41:13 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
3815 | 5000 | Richards Town RWA |  | Tarring of mud/unpaved roads | The place opposite to Clarence school and in front of telaga church has lot of pothole | Rhamannarbrua kumar | Rhamannarbrua kumar_rwauser@mailinator.com | Mobility - Roads, Public transport | Clarke road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 13:08:29 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
3817 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Road is always dug up and not been repaired for a long time | Deepak Pinto | dpinto@zenithprecision.in | Mobility - Roads, Public transport | Pottery road (near Tannery road ) | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 13:46:18 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
3820 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | 1. Hall road extends from E5 BESCOM office to Firdous mosque 2. Davis road from Hutchins road - intersection to Alphonse school | K.g.shashidhar | kg.shashidhar@gmail.com | Mobility - Roads, Public transport | Hall road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 13:55:49 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
3824 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Holy ghost church to pottery road and potholes | P Dinesh soni | dineshsoni479@yahoo.com | Mobility - Roads, Public transport | John Armstrong road, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:07:06 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
3829 | 5000 | Richards Town RWA |  | Tarring of mud/unpaved roads | Road has not been tarred for about 7-8 years. pavements are not maintained. | Annu | annualexander16@hotmail.com | Mobility - Roads, Public transport | 34, Viviani road (dead end) Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:17:21 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
4898 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Very bad condition for a long time (war cookson road) | Clarie Pinto | clariejohn@yahoo.com | Mobility - Roads, Public transport | Richards town area- Hall road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:31:30 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
4907 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Digging across the road occurs with out information the authorities or despite objections by new buildings cake generation etc, water pipe laying has also caused it to dug up along the roads, but tarring never follows leaving the road uneven, causing traffic to slow down and creating problem on a busy road | Evie Kelton | evieta1999@yahoo.com | Mobility - Roads, Public transport | Davis road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:56:37 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
4924 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | That road was dug up for pipeline laying done years ago. It is a shame that nothing has been done to re-tar it | Anaheeta Pinto | anaheetapinto14@gmail.com | Mobility - Roads, Public transport | Hutchins road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:36:06 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | The two issues don’t come under the jurisdiction of the ward
4931 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Sunar murthy road takes a large volume of traffic and from the junction of mouna guru mutt road to Assaye road, The surface is almost un motor able. | Alex Jacob | alex0109@rediffmail.com | Mobility - Roads, Public transport | Cox town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:55:27 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF!
4935 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Pot hole ridden roads are continuing to slower moment of traffic - especially at signals . once it turns green, vehicles are slow out of the blocks covering to pot holes. Really had areas | Jacob Alexander | jacob.alexander@law.christuniversity.in | Mobility - Roads, Public transport | All over the city, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 17:03:13 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60 |  | Nagarothana grant will cover these issues and work will be started in 2-3 weeks | AE - Krishnamurthy | By 30th June
4936 | 5000 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Pot hole ridden roads are continuing to slower moment of traffic - especially at signals . once it turns green, vehicles are slow out of the blocks covering to pot holes. Really had areas | Jacob Alexander | jacob.alexander@law.christuniversity.in | Mobility - Roads, Public transport | All over the city, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 17:03:13 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
4868 | 5003 | Richards Town RWA | Tarring of pothole-ridden roads | Tarring of pothole-ridden roads | Hall road, Davis road, Cookson road, John Armstrong road | K G Shashidhar | Richards_T_98@ichangemycity.com | Mobility - Roads, Public transport | Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:41:21 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
4677 | 20000 | - | Tarring of pothole-ridden roads Sagayarapuram ward | Tarring of pothole-ridden roads | The roads should be widened and they are many potholes inthe area which should be fixed | Saniya Khaleel | saniya.khaleel@yahoo.in | Mobility - Roads, Public transport |  | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-12 18:13:14 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
5029 | 20000 | - | Tarring of mud/unpaved roads Sagayarapuram ward | Tarring of mud/unpaved roads | Davis Road - the whole stretch is dug for laying drain pipe lines, and left untarred for past 10 months. Needs attention especially at the junction Davis Road - John Armstrong road, where its pathetic. Inpsite of my repeated complaints, nothing is done so far. its really unfortunate. | Latha | latlr62@ymail.com | Mobility - Roads, Public transport |  | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-16 12:46:59 | Mobility | Road Related Works | Asphalting and tarring works | Mobility -Road Related Works-Asphalting and tarring works | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
4937 | 5000 | Richards Town RWA | Provision for parking | Provision for parking | Several areas of the city need multi level parking | Jacob Alexander | jacob.alexander@law.christuniversity.in | Mobility - Roads, Public transport | All over the city, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 17:03:58 | Mobility | Road Related Works | Parking | Mobility-Road Related Works-Parking | Mobility-Road Related Works | #REF! | #REF! | 19 | Covered under P1771 | [15 empty] | 60
3830 | 5000 | Richards Town RWA | Lane marking and Road signages | Lane marking and Road signages | no signages | Annu | annualexander16@hotmail.com | Mobility - Roads, Public transport | 34, Viviani road (dead end) Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:17:51 | Mobility | Road Related Works | Signages & Lane Markings | Mobility -Road Related Works-Signages & Lane Markings | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
4916 | 5000 | Richards Town RWA | Lane marking and Road signages | Lane marking and Road signages | This abbation was supposed to be moved out of town many years back but nothing has happened . It smells a lot and we have goats and other live stocks being taken on our roads to this place | Lisa Saldanha | lisajoyfernandis@gmail.com | Mobility - Roads, Public transport | Slaughter house on pottery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:17:24 | Mobility | Road Related Works | Signages & Lane Markings | Mobility -Road Related Works-Signages & Lane Markings | Mobility-Road Related Works | #REF! | #REF! | #REF! | Issue description does not match the category. Solution for the category is covered under the Nagorathana grants
4925 | 5000 | Richards Town RWA | Lane marking and Road signages | Lane marking and Road signages | A proper signage is required near the pottery road- Clarence school - over bridge junction for proper management of traffic | Latha Vijayan | latha@cbeyond.in | Mobility - Roads, Public transport | Over bridge on pottery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:39:10 | Mobility | Road Related Works | Signages & Lane Markings | Mobility -Road Related Works-Signages & Lane Markings | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
4872 | 5003 | Richards Town RWA | Lane marking and Road signages | Lane marking and Road signages | Roads mentioned above in sub category B | K G Shashidhar | Richards_T_98@ichangemycity.com | Mobility - Roads, Public transport | Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:42:22 | Mobility | Road Related Works | Signages & Lane Markings | Mobility -Road Related Works-Signages & Lane Markings | Mobility-Road Related Works | #REF! | #REF! | #REF! | Covered under P1771 | [15 empty] | 60
Ward 60 : Budget Category: Pedestrian Related Road Works
3772 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | The footpath is unwalkable due to broken paving, parking of two wheelers and cars on the pavements and garbage | sunita | sunita.vaznaik@hotmail.com | Mobility - Roads, Public transport | Viviani road along habitat serenity | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:20:41 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | P0029 | Street Lighting Charges | Mobility | Pedestrian Related Road Works | Streetlighting |  |  | Sagayarapuram | 60 | 3030303.0303 | 0 | 0 | 0 | 3030303.0303 | Mobility - Roads, Public transport | Installation of mast light at a busy road (main road) junction | 60 | Based on the requirement of ensuring quality of work to be monitored proactively, it was suggested to the BBMP AE – Mr Krishnamurthy to put up the details of a tender once it has been approved. A start date and an end date for every work | Desilting work is in progress and all pedestrian work will be completed before road related works. P1771 has money allocated for both road and pedestrian related work.The road works are slated to be completed in 2-3 weeks. | AE - Krishnamurthy | By 30th June
3805 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | Complete Viviani road | Daphne Carvalho | Daphne Carvalho_rwauser@mailinator.com | Mobility - Roads, Public transport | Viviani road, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 12:18:02 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | P0300 | M & R to Street Lights - Replacement of Burnt Bulbs etc. (Package) | Mobility | Pedestrian Related Road Works | Streetlighting |  |  | Sagayarapuram | 60 | 1186868.6869 | 454505.0505 | 257752.5253 | 0 | 1899126.2626 | Mobility - Roads, Public transport | Installation of mast light at a busy road (main road) junction | 60
3810 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | All the footpaths in Richards town especially in Viviani road and Davis road | E T Ponnukuttan | chandkuttan1934@dataone.com | Mobility - Roads, Public transport | Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 12:46:30 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | P1828 | Provision of Additional Fittings Streetlights (Old Ward Rs.1 Lakhs, New Ward Rs.2 Lakhs) | Mobility | Pedestrian Related Road Works | Streetlighting |  |  | Sagayarapuram | 60 | 0 | 505.0505 | 105530.303 | 0 | 106035.3535 | Mobility - Roads, Public transport | Construction of new footpaths | 60
4889 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | Most of our foot paths are very uneven and the stones are loose. It is very difficult to walk | Kavya Pinto | kavya.pinto@yahoo.com | Mobility - Roads, Public transport | Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:20:10 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | P1771 | Zone Works - POW Works (Ward wise maintenance per Ward Rs.10 lakhs) | Mobility | Pedestrian Related Road Works |  |  |  | Sagayarapuram | 60 | 11742424.2424 | 1893939.3939 | 2272727.2727 | 0 | 15909090.9091 | Mobility - Roads, Public transport | Installation of mast light at a busy road (main road) junction | 60
4894 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | Very bad condition it is not safe to walk | Snehalatha Naidu | snehaism@gmail.com | Mobility - Roads, Public transport | Viviani road / Armstrong road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:25:47 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | P3075 | Special Comprehensive Development Works in Bangalore city (Bangalore city incharge Minister's Discretionary Grants) | Mobility | Pedestrian Related Road Works |  |  |  | Sagayarapuram | 60 | 6313131.3131 | 13333.3333 | 87401.5152 | 0 | 6413866.1616 | Mobility - Roads, Public transport | Construction of new footpaths | 60
4900 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | Footpath is very uneven and dangerous for older people to walk | Clarie Pinto | clariejohn@yahoo.com | Mobility - Roads, Public transport | Viviani Road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:37:26 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | [16 empty] | 60
4911 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | Footpaths are very bad condition | Ahmed ali | Ahmed ali_rwauser@mailinator.com | Mobility - Roads, Public transport | All roads in Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:07:59 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | [16 empty] | 60
4912 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | Footpaths are very bad condition | Ahmed ali | Ahmed ali_rwauser@mailinator.com | Mobility - Roads, Public transport | All roads in Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:07:59 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | [16 empty] | 60
4919 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | We do not have safe and walk able foot paths on any roads | Lisa Saldanha | lisajoyfernandis@gmail.com | Mobility - Roads, Public transport | All roads in Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:24:07 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | [16 empty] | 60
4922 | 5000 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | The footpath works was done in a shoddy manner since years ago. Also many properties have encroached on footpath and made planters / steps over the drain covers. | Anaheeta Pinto | anaheetapinto14@gmail.com | Mobility - Roads, Public transport | Viviani road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:33:33 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | [16 empty] | 60
4873 | 5003 | Richards Town RWA | Repair of existing footpaths | Repair of existing footpaths | Davis road, Viviani road | K G Shashidhar | Richards_T_98@ichangemycity.com | Mobility - Roads, Public transport | Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:43:05 | Mobility | Pedestrian Related Road Works | Footpaths & Side-walks | Mobility -Pedestrian Related Road Works-Footpaths & Side-walks | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | [16 empty] | 60
4896 | 5000 | Richards Town RWA | Installation of streetlights | Installation of streetlights | Not enough street lighting in this area | Snehalatha Naidu | snehaism@gmail.com | Mobility - Roads, Public transport | Near Richards park | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:27:22 | Mobility | Pedestrian Related Road Works | Streetlighting | Mobility -Pedestrian Related Road Works-Streetlighting | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | [16 empty] | 60
4915 | 5000 | Richards Town RWA | Installation of streetlights | Installation of streetlights | Very bad lighting on most of our roads | Ahmed ali | Ahmed ali_rwauser@mailinator.com | Mobility - Roads, Public transport | Most parts of Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:11:42 | Mobility | Pedestrian Related Road Works | Streetlighting | Mobility -Pedestrian Related Road Works-Streetlighting | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | [16 empty] | 60
4918 | 5000 | Richards Town RWA | Installation of streetlights | Installation of streetlights | The area is very badly lit which leads to anti social elements gathering near the place | Lisa Saldanha | lisajoyfernandis@gmail.com | Mobility - Roads, Public transport | Richards park and surrounding area | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:23:17 | Mobility | Pedestrian Related Road Works | Streetlighting | Mobility -Pedestrian Related Road Works-Streetlighting | Mobility-Pedestrian Related Road Works | #REF! | #REF! | #REF! | [16 empty] | 60
Ward 60: Budget Category: Recreational Amenities
4886 | 5000 | Richards Town RWA | Construction of public parks/playgrounds | Construction of public parks/playgrounds | We do not have a space to play | K G Shashidhar | Richards_T_98@ichangemycity.com | Environment | Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:13:09 | Public Amenities | Recreational Amenities |  | Public Amenities-Recreational Amenities- | Public Amenities-Recreational Amenities | #REF! | #REF! | #REF! | P0088 | Maintenance & Management of Parks on Contract | Public Amenities | Recreational Amenities | Parks |  |  | Sagayarapuram | 60 | 2215189.8734 | 534177.2152 | 0 | 0 | 2749367.0886 | Environment | Construction of public parks/playgrounds | 60 |  |  | Horticulture officer:
4914 | 5000 | Richards Town RWA | Construction of public parks/playgrounds | Construction of public parks/playgrounds | We do not have any playground in this area | Ahmed ali | Ahmed ali_rwauser@mailinator.com | Environment | Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:11:00 | Public Amenities | Recreational Amenities |  | Public Amenities-Recreational Amenities- | Public Amenities-Recreational Amenities | #REF! | #REF! | #REF! | P0299 | Drilling & Maintenance of Borewells, Pumpsets & Pipe lines, Erection & Installation maintenance only | Public Amenities | Recreational Amenities | Parks |  |  | Sagayarapuram | 60 | 85714.2857 | 0 | 0 | 0 | 85714.2857 | Environment | Construction of public parks/playgrounds | 60 |  | Horticulture officer mentioned that a borewell has been placed and water was found at a level of 6 inches.
4878 | 5003 | Richards Town RWA | Maintenance of existing public parks/playgrounds | Maintenance of existing public parks/playgrounds | Maintenance of Richards park and borewell facility to provide water | K G Shashidhar | Richards_T_98@ichangemycity.com | Environment | Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:47:44 | Public Amenities | Recreational Amenities |  | Public Amenities-Recreational Amenities- | Public Amenities-Recreational Amenities | #REF! | #REF! | #REF! | P0973 | Lighting of Parks, Toilet Amenities | Public Amenities | Recreational Amenities | Parks |  |  | Sagayarapuram | 60 | 0 | 0 | 0 | 14285.7143 | 14285.7143 | Environment | Construction of public parks/playgrounds | 60
[25 empty] | P1885 | Purchase of Inputs for Parks maintained by BBMP & Inputs for Indoor gardening | Public Amenities | Recreational Amenities | Parks |  |  | Sagayarapuram | 60 | 7428.5714 | 0 | 0 | 0 | 7428.5714 | Environment | Construction of public parks/playgrounds | 60
[25 empty] | P1543 | CDP of Playgrounds | Public Amenities | Recreational Amenities | Playgrounds |  |  | Sagayarapuram | 60 | 0 | 0 | 6232.3232 | 0 | 6232.3232 | Environment | Construction of public parks/playgrounds | 60
Note on AE8: Shobana Venkatasubbu: Category allocation Rationale TBD
Note on AG8: Shobana Venkatasubbu: City/Zone/Area/Division/Ward/Street

## No P codes alloted for inputs
MINUTES OF MEETING- WARD 60 ; 4 June 2016 : No Pcodes alloted for inputs received on MyCityMyBudget
Request Id | source Id | RWA Name | Sub Category | Request Title | Request Description | User Name | Email Id | Category Name | Location | Ward No | Ward Name | Agency | AC | PC | Vote Up Count | Creadted Date | Budget Head | Budget Category | Budget Sub-category | Key1 | Key2 | Match in budget Key1? | Match in budget Key2? | Count of Data in MCMB | Ward No. | Additional points raised by residents | Action points | Responsibility | Timeline
Ward 60 : Budget Category: Heritage Sites
3796 | 5000 | Richards Town RWA | Renovation & preservation of heritage sites |  | Richards park is a heritage site and required to be preserved and up-keep needs to be done. | Suresh Varghese | varghesesuresh@yahoo.com | Heritage Sites | Richards park | 60 | #VALUE! | Bruhat Bengaluru Mahanagara Palike | #VALUE! | Bangalore North | - | 2016-01-11 11:37:01 | Community Infrastructure | Heritage Sites |  | Community Infrastructure-Heritage Sites- | Community Infrastructure-Heritage Sites | #REF! | #REF! | #REF! | 60 | None | None | - | -
3811 | 5000 | Richards Town RWA | Renovation & preservation of heritage sites |  | Renovation of all lights inside the park | E T Ponnukuttan | chandkuttan1934@dataone.com | Heritage Sites | Richards park | 6000000 | #VALUE! | Bruhat Bengaluru Mahanagara Palike | #VALUE! | Bangalore North | - | 2016-01-11 12:49:48 | Community Infrastructure | Heritage Sites |  | Community Infrastructure-Heritage Sites- | Community Infrastructure-Heritage Sites | #REF! | #REF! | #REF! | 60
4910 | 5000 | Richards Town RWA | Renovation & preservation of heritage sites |  | There needs to be some awareness created about the heritage of this area | Evie Kelton | evieta1999@yahoo.com | Heritage Sites | Old houses and the park | 60 | #VALUE! | Bruhat Bengaluru Mahanagara Palike | #VALUE! | Bangalore North | - | 2016-01-13 16:05:30 | Community Infrastructure | Heritage Sites |  | Community Infrastructure-Heritage Sites- | Community Infrastructure-Heritage Sites | #REF! | #REF! | #REF! | 60
Ward 60: Budget Category: Electrical Poles - M & D works
3187 | 20000 | - | Repair of transformers/ electric poles | Repair of transformers/ electric poles Sagayarapuram ward | when i go for a walk around 9 am, often notice that street lights are on, especially on lazare road, cline road and lloyd road. I tried calling up the lazare road KEB office, nobody picks my call. we can save energy if the lights are switched off after 6am. | Latha | latlr62@ymail.com | Electricity & Power | lazare road, cline road | 60 | #VALUE! | Bangalore Electricity Supply Company | #VALUE! | Bangalore North | - | 2015-12-29 09:27:35 | Electricity & Power | Electrical Poles - M & D works |  | Electricity & Power-Electrical Poles - M & D works- | Electricity & Power-Electrical Poles - M & D works | #REF! | #REF! | #REF! | 60 | None | The Engineer responsible for streetlights mentioned that BBMP and BESCOM are working to provide switch controls for the lights which will be completed within 10 days. After that there will auto timers will be installed. | AE - Krishnamurthy | 20-06-2016
Ward 60: Budget Category: Green Cover
4929 | 5000 | Richards Town RWA | Plant new tree saplings |  | The existing trees are probably heading towards the end of their life cycle. corrected pavements must be cut open to a diameter of 1.5-2.0M and trees planted | Alex Jacob | alex0109@rediffmail.com | Environment | Richards Town, 34, Viviani road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:47:05 | Environment | Green Cover |  | Environment-Green Cover- | Environment-Green Cover | #REF! | #REF! | #REF! | 60 | A citizen initiative to count the number of old tress to be pruned and also suggest areas where sapling plantation can be done was suggested . | Volunteers are requested to connect with Mr Shashidhar to form a group and see through the activity end to end | Mr. Shashidhar (Resident) | 2016-06-30
4941 | 5000 | Richards Town RWA | Plant new tree saplings |  | The city has last a considerable number of trees. Area and layout to be planned with trees along the footpath | Jacob Alexander | jacob.alexander@law.christuniversity.in | Environment | All over the city | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 17:09:12 | Environment | Green Cover |  | Environment-Green Cover- | Environment-Green Cover | #REF! | #REF! | #REF! | 60
Ward 60: Budget Category: Lakes
4930 | 5000 | Richards Town RWA | Cleaning and rejuvenation of lakes | Cleaning and rejuvenation of lakes | The narrow strip of canal like land alongside gangadhar junction, should be made into a large STP the treated water should flow into the lake. Strictly no plastics / paper bags/ bottles to be allowed beyond the entry point. Ganesha statue sizes to be limited to 450MM max | Alex Jacob | alex0109@rediffmail.com | Environment | Ulsoor lake | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:52:36 | Public Amenities | Lakes | Lake M&D Works | Public Amenities-Lakes-Lake M&D Works | Public Amenities-Lakes | #REF! | #REF! | #REF! | 60 | NA | This has been taken off since it does not belong to the ward | NA | NA
Ward 60: Budget Category: Safety & Crime
3799 | 5000 | Richards Town RWA | Increase police beat patrolling |  | Increase police beat patrolling | Sheelu Thomas | thomas_sheelu@yahoo.com | Safety and Crime | Richards park | 60 | Sagayarapuram | Bangalore City Police | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:43:35 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60 | Not discussed since there were no police personnel in the meeting. Efforts will be made to get them for the next meeting |  | Citizen meeting every 3rd Saturday at Pulakeshi Nagar PS. residents to join and highlight traffic related complaints in the meeting | NA
3800 | 5000 | Richards Town RWA | Install surveillance cameras | Install surveillance cameras | Install surveillance cameras | Sheelu Thomas | thomas_sheelu@yahoo.com | Safety and Crime | Richards park | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:44:36 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
3812 | 5000 | Richards Town RWA | Increase police beat patrolling |  | Patrolling at Richards town especially in hall road near Firdoze mosque ( The residents of the locality are disturbed by anti-social elements during nights) | E T Ponnukuttan | chandkuttan1934@dataone.com | Safety and Crime | Richards town | 60 | Sagayarapuram | Bangalore City Police | Pulakeshinagar | Bangalore North | - | 2016-01-11 12:53:01 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
3814 | 5000 | Richards Town RWA | Install surveillance cameras | Install surveillance cameras | Install surveillance cameras near the over bridge at the end of Clarke road | Rhamannarbrua kumar | Rhamannarbrua kumar_rwauser@mailinator.com | Safety and Crime | Viviani road, Clarke road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 13:04:27 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
3819 | 5000 | Richards Town RWA | Introduce neighbourhood policing | Introduce neighbourhood policing | We need to get the neighbourhood people involved with police in patrolling our area. | Deepak Pinto | dpinto@zenithprecision.in | Safety and Crime | Richards town | 60 | Sagayarapuram | Bangalore City Police | Pulakeshinagar | Bangalore North | - | 2016-01-11 13:52:13 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
3835 | 5000 | Richards Town RWA | Increase police beat patrolling |  | Lot of chain snatching, teenagers drinking and doing drugs at the end of our road, Please increase police surveillance and beat | Annu | annualexander16@hotmail.com | Safety and Crime | 34, Viviani road, Richards town | 60 | Sagayarapuram | Bangalore City Police | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:30:26 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
3836 | 5000 | Richards Town RWA | Introduce neighbourhood policing | Introduce neighbourhood policing | Lot of chain snatching, teenagers drinking and doing drugs at the end of our road, Please increase police surveillance and beat | Annu | annualexander16@hotmail.com | Safety and Crime | 34, Viviani road, Richards town | 60 | Sagayarapuram | Bangalore City Police | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:30:43 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
3837 | 5000 | Richards Town RWA | Install surveillance cameras | Install surveillance cameras | Lot of chain snatching, teenagers drinking and doing drugs at the end of our road, Please increase police surveillance and beat | Annu | annualexander16@hotmail.com | Safety and Crime | 34, Viviani road, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:30:59 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
4887 | 5000 | Richards Town RWA | Increase police beat patrolling |  | We have a lot of boys that hang around near the park and pass comments when we pass by | K G Shashidhar | Richards_T_98@ichangemycity.com | Safety and Crime | Near Richards park | 60 | Sagayarapuram | Bangalore City Police | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:15:05 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
4920 | 5000 | Richards Town RWA | Increase police beat patrolling |  | Several incidents of harassment and chain snatching /phone snatching by young persons on motorbikes, although its a busy road. increased police presence on this stretch can make these persons way and enable the police to nab culprits | Anaheeta Pinto | anaheetapinto14@gmail.com | Safety and Crime | John Armstrong road | 60 | Sagayarapuram | Bangalore City Police | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:29:55 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
4921 | 5000 | Richards Town RWA | Increase police beat patrolling |  | Several incidents of harassment and chain snatching /phone snatching by young persons on motorbikes, although its a busy road. increased police presence on this stretch can make these persons way and enable the police to nab culprits | Anaheeta Pinto | anaheetapinto14@gmail.com | Safety and Crime | John Armstrong road | 60 | Sagayarapuram | Bangalore City Police | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:30:00 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
4928 | 5000 | Richards Town RWA | Introduce neighbourhood policing | Introduce neighbourhood policing | There is a need for more serenity in the area to keep away unwanted elements | Latha Vijayan | latha@cbeyond.in | Safety and Crime | 34, Viviani road, Richards Town | 60 | Sagayarapuram | Bangalore City Police | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:43:02 | Safety & Crime |  |  | Safety & Crime-- | Safety & Crime- | #REF! | #REF! | #REF! | 60
3776 | 5000 | Richards Town RWA | Fogging and Pest control |  | Poses a severe health hazards in its present condition | sunita | sunita.vaznaik@hotmail.com | Public health | Slaughter house on pottery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:22:13 | Sanitation | Pest Control |  | Sanitation-Pest Control- | Sanitation-Pest Control | #REF! | #REF! | #REF! | 60 | No additional points | Health Inspector from BBMP mentioned that Fogging is carried out once a week per ward. It was deicided to take signatures of Mr Soni ( citizen who highlighted the issue) when fogging is carried out in the area. | Health Inspector - Venkatesh | Once every week
3795 | 5000 | Richards Town RWA | Fogging and Pest control |  | Fogging and pest control | Suresh Varghese | varghesesuresh@yahoo.com | Public health | Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:35:43 | Sanitation | Pest Control |  | Sanitation-Pest Control- | Sanitation-Pest Control | #REF! | #REF! | #REF! | 60
3801 | 5000 | Richards Town RWA | Fogging and Pest control |  | Fogging and pest control | Sheelu Thomas | thomas_sheelu@yahoo.com | Public health | Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:45:15 | Sanitation | Pest Control |  | Sanitation-Pest Control- | Sanitation-Pest Control | #REF! | #REF! | #REF! | 60
3804 | 5000 | Richards Town RWA | Fogging and Pest control |  | Rats, Mosquitoes on Rogers road around Richards town | Shubha Shetty | Shubha Shetty_rwauser@mailinator.com | Public health | Rogers road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:58:16 | Sanitation | Pest Control |  | Sanitation-Pest Control- | Sanitation-Pest Control | #REF! | #REF! | #REF! | 60
3808 | 5000 | Richards Town RWA | Fogging and Pest control |  | Fogging and pest control | Daphne Carvalho | Daphne Carvalho_rwauser@mailinator.com | Public health | Viviani road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 12:32:28 | Sanitation | Pest Control |  | Sanitation-Pest Control- | Sanitation-Pest Control | #REF! | #REF! | #REF! | 60
3834 | 5000 | Richards Town RWA | Fogging and Pest control |  | Our conservancy lanes the breeding grounds for mosquitoes and rats many people are affected with Dengue, Chikengunya. Conservancy lanes are full of weeds, Bandicoots are entering the houses. Please clear the conservancy lanes and keep it clean | Annu | annualexander16@hotmail.com | Public health | 34, Viviani road, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:28:09 | Sanitation | Pest Control |  | Sanitation-Pest Control- | Sanitation-Pest Control | #REF! | #REF! | #REF! | 60
4927 | 5000 | Richards Town RWA | Fogging and Pest control |  | There is no fogging and pest control in and around our area. There is a huge rat menace that needs to be controlled | Latha Vijayan | latha@cbeyond.in | Public health | 34, Viviani road, Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:41:24 | Sanitation | Pest Control |  | Sanitation-Pest Control- | Sanitation-Pest Control | #REF! | #REF! | #REF! | 60
Ward 60 : Budget Category: Public Toilets
4917 | 5000 | Richards Town RWA | Construction of public toilets |  | We dont have a public toilet in this area and so men relieve themselves on the compound walls | Lisa Saldanha | lisajoyfernandis@gmail.com | Public Utilities and services | Pottery road (near East railway station) | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:20:44 | Sanitation | Public Toilets |  | Sanitation-Public Toilets- | Sanitation-Public Toilets | #REF! | #REF! | #REF! | 60 |  | AE mentioned that this may not be possible , because of lack of space. But he agreed to carry out an inspection for an alternative. | AE - Krishnamurthy | 2016-06-30
4942 | 5000 | Richards Town RWA | Maintenance of public toilets | Maintenance of public toilets | Public toilets used to be maintained well. as of now , poor maintenance | Jacob Alexander | jacob.alexander@law.christuniversity.in | Public Utilities and services | All over the city, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 17:10:46 | Sanitation | Public Toilets |  | Sanitation-Public Toilets- | Sanitation-Public Toilets | #REF! | #REF! | #REF! | 60
4884 | 5003 | Richards Town RWA | Construction of public toilets | Construction of public toilets | Public toilet at east railway station entrance- Pl 2 side | K G Shashidhar | Richards_T_98@ichangemycity.com | Public Utilities and services | Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:59:10 | Sanitation | Public Toilets |  | Sanitation-Public Toilets- | Sanitation-Public Toilets | #REF! | #REF! | #REF! | 60
Ward 60: Budget Category: Sewage
3828 | 5000 | Richards Town RWA | Maintanence of sewage lines | Maintanence of sewage lines | As above mentioned with the technical work of quality ensured | P Dinesh soni | dineshsoni479@yahoo.com | Sanitation | John Armstrong road to Richards town | 60 | Sagayarapuram | Bangalore Water Supply and Sewerage Board | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:14:08 | Sanitation | Sewage | Sewage Lines - M&D | Sanitation-Sewage-Sewage Lines - M&D | Sanitation-Sewage | #REF! | #REF! | #REF! | 60 | NA | Regular maintenance of sewege lines is being carried out. In the case of conservancy lines, these have been constructed long back, and this issue will be sorted after the construction of new manholes. | BWSSB AE- Lordlay Lathal Sab | 2016-07-30
4902 | 5000 | Richards Town RWA | Construction of sewage lines | Construction of sewage lines | Since my building ' Edward house' is at the bottom of the slope from Davis road to Pottery road and because of the sewage pipeline, sewage over flows regularly in the conservancy lane, very quickly flood up our basement. This is a health hazard for residents since we are unable to clean todays | Evie Kelton | evieta1999@yahoo.com | Sanitation | Pottery road | 60 | Sagayarapuram | Bangalore Water Supply and Sewerage Board | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:44:06 | Sanitation | Sewage | Sewage Lines - M&D | Sanitation-Sewage-Sewage Lines - M&D | Sanitation-Sewage | #REF! | #REF! | #REF! | 60
4881 | 5003 | Richards Town RWA | Construction of sewage lines | Construction of sewage lines | Desillting and repair of storm water drain. Starting from Davis road and ending at pottery road near Slaughter house | K G Shashidhar | Richards_T_98@ichangemycity.com | Sanitation | Richards Town | 60 | Sagayarapuram | Bangalore Water Supply and Sewerage Board | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:51:07 | Sanitation | Sewage | Sewage Lines - M&D | Sanitation-Sewage-Sewage Lines - M&D | Sanitation-Sewage | #REF! | #REF! | #REF! | 60 | NA | BWSSB central office provides the desilting program. The Desilting program list to be shared. | BWSSB AE- Lordlay Lathal Sab
4882 | 5003 | Richards Town RWA | Maintanence of sewage lines | Maintanence of sewage lines | Existing sewage lines and chambers to be increased ( Viviani road, pottery road and Davis road) | K G Shashidhar | Richards_T_98@ichangemycity.com | Sanitation | Richards Town | 60 | Sagayarapuram | Bangalore Water Supply and Sewerage Board | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:53:27 | Sanitation | Sewage | Sewage Lines - M&D | Sanitation-Sewage-Sewage Lines - M&D | Sanitation-Sewage | #REF! | #REF! | #REF! | 60 | NA | Regular maintenance of sewege lines is being carried out. Conservancy lines have been constructed long back, and this issue will be sorted after the construction of new manholes. | BWSSB AE- Lordlay Lathal Sab | 2016-07-30
2257 | 20000 | - | Maintanence of sewage lines | Maintanence of sewage lines Sagayarapuram ward | The Tannery road is always being dug up multiple times and stinks of bad sewage. Needs immediate attention in finding a permanent solution for this issue. | Chaitanya Tupaki | chaits.ts@gmail.com | Sanitation |  | 60 | Sagayarapuram | Bangalore Water Supply and Sewerage Board | Pulakeshinagar | Bangalore North | - | 2015-12-17 13:42:19 | Sanitation | Sewage | Sewage Lines - M&D | Sanitation-Sewage-Sewage Lines - M&D | Sanitation-Sewage | #REF! | #REF! | #REF! | 60
Ward 60: Budget Category: Storm Water Drains
3807 | 5000 | Richards Town RWA | Desilting of Storm water Drains | Desilting of Storm water Drains | Desilting of storm water drains | Daphne Carvalho | Daphne Carvalho_rwauser@mailinator.com | Sanitation | Viviani road | 60 | Sagayarapuram | Bangalore Water Supply and Sewerage Board | Pulakeshinagar | Bangalore North | - | 2016-01-11 12:31:56 | Sanitation | Storm Water Drains | Storm Water Drain Works | Sanitation-Storm Water Drains-Storm Water Drain Works | Sanitation-Storm Water Drains | #REF! | #REF! | #REF! | 60 | NA | AE mentioned that a tender has been called but no contract awarded since no contractor agreeing to take up the work. Budget of 1.30Cr available. | AE - Krishnamurthy | update in next meeting
Ward 60: Budget Category: Garbage Collection & Composting
3793 | 5000 | Richards Town RWA | Build composting units | Build composting units | Waste of slaughter house is currently dumped randomly causing foul smell in the neighbourhood if a composting unit is provided the waste can be put to good use | Suresh Varghese | varghesesuresh@yahoo.com | Solid waste management | Doddi (Slaughter house) at Tannery road and Pottery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:31:05 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60 |  | To build a composting unit an estimate has been sent by the AE and is awaiting sanction | AE - Krishnamurthy | 2016-06-30
3798 | 5000 | Richards Town RWA | Build composting units | Build composting units | Build composting unit | Sheelu Thomas | thomas_sheelu@yahoo.com | Solid waste management | Doddi (slaughter house) tannery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:41:56 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60
3821 | 5000 | Richards Town RWA | Require regular Door to door garbage collection |  | Door ti door collection littering block spot avoidances at John Armstrong road, pottery road | K.g.shashidhar | kg.shashidhar@gmail.com | Solid waste management | Ward - B60 - Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 13:58:57 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60 |  | AE has shared his number, and has asked citizens to call in case door to door collection does not happen regularly. The contractor is scheduled to change in the next month and a new contractor will be doing the job. The number of autos will also be increased. | AE - Krishnamurthy AND Health Inspector - Venkatesh | As and when issue is noticed
3822 | 5000 | Richards Town RWA | Build composting units | Build composting units | Composting/ Bio-methanol can do set on Clarence school ground | K.g.shashidhar | kg.shashidhar@gmail.com | Solid waste management | Ward 60 -B | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:01:14 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60 |  | To build a composting unit an estimate has been sent by the AE and is awaiting sanction | AE - Krishnamurthy | 2016-06-30
3831 | 5000 | Richards Town RWA | Require regular Door to door garbage collection |  | Garbage is not being collected regularly | Annu | annualexander16@hotmail.com | Solid waste management | 34, Viviani road, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:19:25 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60 |  | AE has shared his number, and has asked citizens to call in case door to door collection does not happen regularly. The contractor is scheduled to change in the next month and a new contractor will be doing the job. The number of autos will also be increased. | AE - Krishnamurthy AND Health Inspector - Venkatesh | As and when issue is noticed
3833 | 5000 | Richards Town RWA | Build composting units | Build composting units | We would like a composting unit at the end of our road to process wet waste and there by reduce waste going to the landfills | Annu | annualexander16@hotmail.com | Solid waste management | 34, Viviani road, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:23:03 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60 |  | To build a composting unit an estimate has been sent by the AE and is awaiting sanction | AE - Krishnamurthy | 2016-06-30
4923 | 5000 | Richards Town RWA | Require regular Door to door garbage collection |  | The garbage collection is irregular | Anaheeta Pinto | anaheetapinto14@gmail.com | Solid waste management | Viviani road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:34:24 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60 |  | AE has shared his number, and has asked citizens to call in case door to door collection does not happen regularly. The contractor is scheduled to change in the next month and a new contractor will be doing the job. The number of autos will also be increased. | AE - Krishnamurthy AND Health Inspector - Venkatesh | As and when issue is noticed
4933 | 5000 | Richards Town RWA | Build composting units | Build composting units | Composting units must be set up in all localities. The whole activity must get to be commercially un able far the people given the responsibility of running it | Alex Jacob | alex0109@rediffmail.com | Solid waste management | All over | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:57:55 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60 |  | To build a composting unit an estimate has been sent by the AE and is awaiting sanction | AE - Krishnamurthy | 2016-06-30
4939 | 5000 | Richards Town RWA | Require regular Door to door garbage collection |  | Garbage is not collected regularly starts accumulating inside the apartment. | Jacob Alexander | jacob.alexander@law.christuniversity.in | Solid waste management | Richards town, Viviani road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 17:05:37 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60 | The contractor is scheduled to change in the next month and a new contractor will be doing the job. The number of autos will also be increased. | Citizens to call AE in case door to door collection does not happen regularly. | AE - Krishnamurthy AND Health Inspector - Venkatesh | As and when issue is noticed
4875 | 5003 | Richards Town RWA | Require regular Door to door garbage collection | Require regular Door to door garbage collection | Door to door garbage collection on daily basis (Solid waste, dry waste, Sanitary waste, garden waste, e-waste) | K G Shashidhar | Richards_T_98@ichangemycity.com | Solid waste management | Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:45:32 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60
4876 | 5003 | Richards Town RWA | Build composting units | Build composting units | Build composting unit on St. Charles school ground | K G Shashidhar | Richards_T_98@ichangemycity.com | Solid waste management | Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 14:46:34 | Solid Waste Management | Garbage Collection & Composting |  | Solid Waste Management -Garbage Collection & Composting- | Solid Waste Management-Garbage Collection & Composting | #REF! | #REF! | #REF! | 60 |  | To build a composting unit an estimate has been sent by the AE and is awaiting sanction | AE - Krishnamurthy | 2016-06-30
Ward 60: Budget Category: SWM Maintenance & Development Works
3803 | 5000 | Richards Town RWA | Maintain cleanliness of streets ( sweeping, removal of debris) | Maintain cleanliness of streets ( sweeping, removal of debris) | Garbage thrown in the end of the road | Shubha Shetty | Shubha Shetty_rwauser@mailinator.com | Solid waste management | Rogers road, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 11:50:53 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60 | NA | AE has shared his number. Can call AE if activity not happening regularly | AE- Krishnamurthy | As and when issue is noticed
3806 | 5000 | Richards Town RWA | Build dry waste collection centres | Build dry waste collection centres | Garbage waste | Daphne Carvalho | Daphne Carvalho_rwauser@mailinator.com | Solid waste management | Viviani road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 12:30:23 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60
3818 | 5000 | Richards Town RWA | Build dry waste collection centres | Build dry waste collection centres | This area needs a collection centre for dry waste collection | Deepak Pinto | dpinto@zenithprecision.in | Solid waste management | Clarke road (at Richards park) | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 13:47:32 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60
3826 | 5000 | Richards Town RWA | Build dry waste collection centres | Build dry waste collection centres | As a mess clean up the proper way | P Dinesh soni | dineshsoni479@yahoo.com | Solid waste management | All over Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:12:54 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60
3832 | 5000 | Richards Town RWA | Maintain cleanliness of streets ( sweeping, removal of debris) | Maintain cleanliness of streets ( sweeping, removal of debris) | Sweeper does not pick up dry leaves on the road. | Annu | annualexander16@hotmail.com | Solid waste management | 34, Viviani road, Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-11 14:21:35 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60
4891 | 5000 | Richards Town RWA | Maintain cleanliness of streets ( sweeping, removal of debris) | Maintain cleanliness of streets ( sweeping, removal of debris) | There is a lot of garbage thrown all over the place | Kavya Pinto | kavya.pinto@yahoo.com | Solid waste management | Armstrong road/ pottery road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:21:14 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60
4893 | 5000 | Richards Town RWA | Maintain cleanliness of streets ( sweeping, removal of debris) | Maintain cleanliness of streets ( sweeping, removal of debris) | Lot of garbage being thrown all over / segregation done on this road | Snehalatha Naidu | snehaism@gmail.com | Solid waste management | Armstrong road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 15:23:52 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60
4909 | 5000 | Richards Town RWA | Build dry waste collection centres | Build dry waste collection centres | This area needs is own dry waste centre which is managed proficiently right now, there is a lot of garbage every day and poor condition. Residents are unable to sustain segregation because of poor support from these entries | Evie Kelton | evieta1999@yahoo.com | Solid waste management | Richards town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:03:50 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60
4926 | 5000 | Richards Town RWA | Maintain cleanliness of streets ( sweeping, removal of debris) | Maintain cleanliness of streets ( sweeping, removal of debris) | Garbage and debris need to be cleaned and collected | Latha Vijayan | latha@cbeyond.in | Solid waste management | 34, Viviani road, Richards Town | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 16:40:00 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60
4940 | 5000 | Richards Town RWA | Maintain cleanliness of streets ( sweeping, removal of debris) | Maintain cleanliness of streets ( sweeping, removal of debris) | Streets are not being cleaned regularly or even if they do, done in a shabby manner | Jacob Alexander | jacob.alexander@law.christuniversity.in | Solid waste management | Richards town, Viviani road | 60 | Sagayarapuram | Bruhat Bengaluru Mahanagara Palike | Pulakeshinagar | Bangalore North | - | 2016-01-13 17:06:40 | Solid Waste Management | SWM Maintenance & Development Works |  | Solid Waste Management -SWM Maintenance & Development Works- | Solid Waste Management-SWM Maintenance & Development Works | #REF! | #REF! | #REF! | 60

## Addtional points raised
MOM: ward sabha : Ward 60 : Additional points raised in the meeting
Issue highlighted | Highlighted by | Question addressed to | Action points | Timeline
Excessive speeding at the junction of Hall road and Cookson road, Davis road and Hall road .Citizens raised the need for speed breakers at these junctions. |  | corporator | Issue to be highlighted in the traffic police meeting at Pulakeshi nagar police station. Approval needs to be given by Traffic police and execution is done by BBMP. Meeting held 3rd Saturday of every month. | 2016-06-18
Hennur road 2nd cross- Ananthram layout – 2years back drainage pipe was laid and there were no manholes built The condition of the road is quite bad since the last two years. No action taken even after several follow ups. | Mr Francis from Hennur cross road | BWSSB | To be responded to in the next meeting | Next ward sabha
No switches for streetlights in Hennur road |  | BESCOM / BBMP
Sundar hospital to Angalaparmeshwari temple road is in a bad shape |  | BBMP
Footpaths on Davis road are difficult for senior citizens to use because of height from road |  | BBMP
receiving calls from young ladies that they are being pestered by antisocial elements in the park. | Mr Joseph from Richards town | Corporator | To be responded to in the next meeting | Next ward sabha
A Effluent treatment plant in the slaughter house was set up 2 years back but is in disuse. The corporator mentioned that there is a lack of funds to run to STP and next steps will be mentioned in the next meeting. |  | BBMP
Debri after a digging near Holy cross church needs to be cleared |  | BBMP