## 1st Apr 2018 31st Mar 2019
SL No | Month | Date | Ward_No | Ward_Name | Sub_Division | Division | Zone | Job_Code | Job_Description | Category | Work_ Order | Work_Order_Date | Sub Bill Register_No | Sub Bill Register_Date | Bill Register No | Bill Register Date | Job Code Year | CBR_No | CBR_Date | Gross_ Amount In Lakhs | Deduction In Lakhs | Nett_ Amount In Lakhs | RTGS_No | RTGS_Date | Contractor Number | Contractor_Name | P_Code | Budget_Head | Budget_ Head_ID | Engineer Details | Gross_ Amount In Cr | Current/Pending /Spill over
75 | April | 2018-04-04 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000021 | Construction of RCC Sump and Improvements to roads and drains at Gruhalakshmi layout and maintenance of Rangamandira at Kuvempu Park in Ward No 74 Shankthiganapathinagar | Roads & Drivablility | 000260 | 2018-02-24 | 000179 | 2018-03-23 | 000303 | 2018-03-23 | 18 | 000166 | 2018-04-03 | 24.9087 | 2.6199 | 22.2888 | 2 | 2018-04-04 | 9900333496 | kridl | P3111 | State Finance Commission Untied Grant Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.24909 | Pending
1122 | May | 2018-05-10 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000001 | Providing water supply and drilling of borewells in ward no.74 | Water & Sanitary | 000182 | 2016-08-19 | 000039 | 2016-12-30 | 000873 | 2017-01-30 | 17 | 001351 | 2018-05-09 | 28.9716 | 4.035 | 24.9366 | 49 | 2018-05-10 | 9900333496 | kridl | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.28972 | Pending
1186 | May | 2018-05-18 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000026 | Improvements of drain culvert and desilting in 2nd Cross 1st main Kuvempu road from Kuvempu circle ch. 150.00 to ward 74 Border in ward NO.74 | Footpaths & Walkability | 000074 | 2016-06-20 | 000190 | 2016-07-29 | 000445 | 2016-08-28 | 16 | 001427 | 2018-05-16 | 19.8008 | 2.7396 | 17.0613 | 52 | 2018-05-18 | 9900333496 | M/s KRIDL | P0190 | Works sanctioned by Hon Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19801 | Pending
1796 | June | 2018-06-06 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000022 | Construction of RCC drains and Footpath both side of Kamalanagara mainroad from Rajkumar Statue to Kevumpu Circle in Ward no -74 Shankthiganapathinagara (CH:300.00 mtr to 400.00mtrs) | Footpaths & Walkability | 000083 | 2016-06-20 | 000265 | 2016-08-26 | 000540 | 2016-09-12 | 16 | 002139 | 2018-06-04 | 19.9663 | 2.6679 | 17.2984 | 71 | 2018-06-06 | 9900333496 | kridl | P0190 | Works sanctioned by Hon Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19966 | Pending
1797 | June | 2018-06-06 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000020 | Construction of RCC drains and Footpath both side of Kamalanagara mainroad from Rajkumar Statue to Kevumpu Circle in Ward no -74 Shankthiganapathinagara (CH:100.00 mtr to 200.00mtrs) | Footpaths & Walkability | 000081 | 2016-06-20 | 000264 | 2016-08-23 | 000542 | 2016-09-12 | 16 | 002140 | 2018-06-04 | 19.9759 | 2.6717 | 17.3042 | 71 | 2018-06-06 | 9900333496 | kridl | P0190 | Works sanctioned by Hon Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19976 | Pending
1798 | June | 2018-06-06 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000034 | Improvements of drain (Gruhalakshmi Layout) in Ward No. 74 | Footpaths & Walkability | 000105 | 2016-07-23 | 000266 | 2016-08-29 | 000544 | 2016-09-12 | 16 | 002141 | 2018-06-04 | 19.8176 | 2.7054 | 17.1122 | 71 | 2018-06-06 | 9900333496 | M/s KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19818 | Pending
1799 | June | 2018-06-06 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000033 | Improvements of Drain, footpath, park (BEML) Layout and Gruhalakshmi Layout) in Ward No. 74 | Footpaths & Walkability | 000104 | 2016-06-23 | 000267 | 2016-08-30 | 000545 | 2016-09-12 | 16 | 002142 | 2018-06-04 | 19.8179 | 2.713 | 17.1049 | 71 | 2018-06-06 | 9900333496 | M/s KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19818 | Pending
1800 | June | 2018-06-06 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-12-000004 | Construction of Yoga Center at Parks in ward no 74 | Trees, Parks & Playgrounds | 000440 | 2013-01-09 | 000162 | 2015-07-31 | 000445 | 2015-07-31 | 12 | 006568 | 2016-03-26 | 0.68101 | 0.08446 | 0.59655 | 71 | 2018-06-06 | 9986316782 | Ms Manoj Enterprises | P2201 | Assembly Constituency Development Works under BBMP | ddo209 | Assistant Executive Engineer Electrical West Zone | 0.0068101 | Pending
2015 | June | 2018-06-11 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000036 | Providing CC road and retaining wall to cross road Near Veteranary Hospital in ward No. 74 | Roads & Drivablility | 000107 | 2016-06-23 | 000288 | 2016-08-28 | 000618 | 2016-09-19 | 16 | 002299 | 2018-06-07 | 19.8175 | 2.7009 | 17.1166 | 80 | 2018-06-11 | 9900333496 | kridl | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19817 | Pending
2016 | June | 2018-06-11 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000035 | Providing RCC drain to Cross road Near Veteranary Hospital in ward No. 74 | Footpaths & Walkability | 000106 | 2016-06-23 | 000287 | 2016-08-03 | 000619 | 2016-09-19 | 16 | 002301 | 2018-06-07 | 19.7857 | 2.7391 | 17.0466 | 80 | 2018-06-11 | 9900333496 | kridl | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19786 | Pending
2017 | June | 2018-06-11 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000009 | Construction of RCC drain with covering slab at 2nd Main from SBI Staff to 1st cross in ward no.74 | Footpaths & Walkability | 000190 | 2016-08-19 | 000292 | 2016-08-29 | 000623 | 2016-09-20 | 17 | 002304 | 2018-06-07 | 27.7313 | 3.9371 | 23.7942 | 80 | 2018-06-11 | 9900333496 | kridl | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.27731 | Pending
2018 | June | 2018-06-11 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000008 | Construction of RCC drain with covering slab at 3rd Cross SBI Staff colony in ward no.74 | Footpaths & Walkability | 000189 | 2016-08-19 | 000291 | 2016-08-29 | 000624 | 2016-09-20 | 17 | 002305 | 2018-06-07 | 27.9766 | 3.9491 | 24.0275 | 80 | 2018-06-11 | 9900333496 | kridl | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.27977 | Pending
2019 | June | 2018-06-11 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000007 | Construction of RCC drain with covering slab at 2nd Cross SBI Staff colony in ward no.74 | Footpaths & Walkability | 000188 | 2016-08-19 | 000290 | 2016-08-29 | 000625 | 2016-09-20 | 17 | 002306 | 2018-06-07 | 27.7095 | 3.8934 | 23.8161 | 80 | 2018-06-11 | 9900333496 | M/s KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.27709 | Pending
2020 | June | 2018-06-11 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000006 | Construction of RCC drain with covering slab at 1st Cross SBI Staff colony in ward no.74 | Footpaths & Walkability | 000187 | 2016-08-19 | 000293 | 2016-09-04 | 000626 | 2016-09-20 | 17 | 002307 | 2018-06-07 | 27.9606 | 3.967 | 23.9936 | 80 | 2018-06-11 | 9900333496 | kridl | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.27961 | Pending
2304 | June | 2018-06-18 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000019 | Construction of RCC drains and Footpath both side of Kamalanagara mainroad from Rajkumar Statue to Kevumpu Circle in Ward no -74 Shankthiganapathinagara (CH:00.00 mtr to 100.00mtrs) | Footpaths & Walkability | 000080 | 2016-06-20 | 000262 | 2016-08-22 | 000543 | 2016-09-12 | 16 | 002347 | 2018-06-11 | 19.9695 | 2.6672 | 17.3023 | 90 | 2018-06-18 | 9900333496 | kridl | P0190 | Works sanctioned by Hon Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19969 | Pending
2547 | June | 2018-06-23 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000021 | Construction of RCC drains and Footpath both side of Kamalanagara mainroad from Rajkumar Statue to Kevumpu Circle in Ward no -74 Shankthiganapathinagara (CH:200.00 mtr to 300.00mtrs) | Footpaths & Walkability | 000082 | 2016-06-20 | 000263 | 2016-08-24 | 000541 | 2016-09-12 | 16 | 002632 | 2018-06-18 | 19.9975 | 2.6732 | 17.3243 | 99 | 2018-06-23 | 9900333496 | kridl | P0190 | Works sanctioned by Hon Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19998 | Pending
2852 | July | 2018-07-02 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000022 | Construction of toilet Block and other development works in Kuvempu Park in ward No 74 | Health & Sanitation | 000261 | 2018-02-24 | 000048 | 2018-06-12 | 000089 | 2018-06-13 | 18 | 003074 | 2018-06-28 | 24.9934 | 2.4296 | 22.5638 | 104 | 2018-07-02 | 9900333496 | kridl | P3111 | State Finance Commission Untied Grant Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.24993 | Spill Over
2853 | July | 2018-07-02 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000012 | Engaging Tractor, Labour, JCB for Maintanace of roads and drains (Silt and Tractor) in Ward No. 74 | Roads & Drivablility | 000008 | 2016-05-06 | 000180 | 2016-06-30 | 000411 | 2016-07-29 | 16 | 009624 | 2018-02-07 | 1.0061 | 0.11167 | 0.89439 | 108 | 2018-07-02 | 0 | T.Rajesh | P1771 | Zone Works - POW Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.010061 | Pending
2854 | July | 2018-07-02 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000012 | Engaging Tractor, Labour, JCB for Maintanace of roads and drains (Silt and Tractor) in Ward No. 74 | Roads & Drivablility | 000008 | 2016-05-06 | 000180 | 2016-06-30 | 000411 | 2016-07-29 | 16 | 009624 | 2018-02-07 | 1.6162 | 0.17938 | 1.4368 | 108 | 2018-07-02 | 0 | T.Rajesh | P1771 | Zone Works - POW Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.016162 | Pending
3159 | July | 2018-07-09 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000005 | Construction of RCC drain with covering slab at 3rd main NHCS Layout in ward no.74 | Footpaths & Walkability | 000186 | 2016-08-19 | 000361 | 2016-12-17 | 000770 | 2016-12-17 | 17 | 003412 | 2018-07-07 | 22.7755 | 3.1655 | 19.61 | 117 | 2018-07-09 | 9900333496 | M/s KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.22776 | Pending
3160 | July | 2018-07-09 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000003 | Construction of RCC drain with covering slab at 2nd main NHCS Layout in ward no.74 | Footpaths & Walkability | 000184 | 2016-08-19 | 000363 | 2016-12-17 | 000771 | 2016-12-17 | 17 | 003413 | 2018-07-07 | 29.6674 | 4.1245 | 25.5429 | 117 | 2018-07-09 | 9900333496 | M/s KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.29667 | Pending
3161 | July | 2018-07-09 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000004 | Construction of RCC drain with covering slab at 1st G main from 1st main to Narasimha murthy house NHCS Layout in ward no.74 | Footpaths & Walkability | 000185 | 2016-08-19 | 000360 | 2016-12-17 | 000772 | 2016-12-17 | 17 | 003414 | 2018-07-07 | 11.8493 | 1.5973 | 10.252 | 117 | 2018-07-09 | 9900333496 | M/s KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.11849 | Pending
3162 | July | 2018-07-09 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000002 | Construction of RCC drain with covering slab at 1st main NHCS Layout in ward no.74 | Footpaths & Walkability | 000183 | 2016-08-19 | 000362 | 2016-12-17 | 000773 | 2016-12-17 | 17 | 003415 | 2018-07-07 | 26.2621 | 3.6494 | 22.6127 | 117 | 2018-07-09 | 9900333496 | M/s KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.26262 | Pending
3294 | July | 2018-07-16 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000024 | Providing CC to cross roads at Chandranagar in ward no 74 Shakthiganapathinagara | Roads & Drivablility | 000349 | 2016-11-16 | 000379 | 2016-12-31 | 000795 | 2016-12-31 | 17 | 003673 | 2018-07-12 | 14.8283 | 2.0192 | 12.8091 | 125 | 2018-07-16 | 9900333496 | M/s KRIDL | P2415 | Reserve fund for TandF Committee | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.14828 | Pending
3511 | July | 2018-07-18 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000058 | Construction of Anganawadi building at Sanjayagandhi nagara in ward No.74 Shakthiganapathinagara | Other Ward Works | 000478 | 2017-03-09 | 000003 | 2017-08-05 | 000007 | 2017-08-05 | 17 | 003803 | 2018-07-13 | 18.0997 | 1.2364 | 16.8633 | 129 | 2018-07-18 | 9448615567 | C.Lokesh | P1771 | Zone Works - POW Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.181 | Pending
3676 | July | 2018-07-19 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000070 | Providing drinking water works in Ward No 74 in Mahalakshmi lyt Division | Drinking Water | 000054 | 2018-06-26 | 000062 | 2018-06-26 | 000131 | 2018-06-27 | 17 | 003748 | 2018-07-13 | 13.47 | 0.338 | 13.132 | 133 | 2018-07-19 | 7899222863 | R.Rathna, | P3110 | 14th Finance Commission Grant Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.1347 | Current
3736 | July | 2018-07-20 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000001 | Annual Operation And maintenance Of Street Lights at Shakthiganapathinagara and Vrushabhavathi nagara in Ward No-74 and 102 | Footpaths & Walkability | 000013 | 2017-07-17 | 000088 | 2018-02-19 | 000116 | 2018-02-19 | 16 | 003948 | 2018-07-18 | 19.212 | 1.9404 | 17.2715 | 134 | 2018-07-20 | 9916368736 | Electrolines | P0300 | M and R to Street Lights - Replacement of Burnt Bulbs etc. (Package) | ddo209 | Assistant Executive Engineer Electrical West Zone | 0.19212 | Pending
3912 | July | 2018-07-24 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000033 | Improvements to drain at 2nd 3rd 4th and 5th main of Sy 46 Kamalanagara in ward no 74 | Footpaths & Walkability | 000357 | 2016-11-18 | 000409 | 2017-01-31 | 000880 | 2017-01-30 | 17 | 004145 | 2018-07-20 | 23.7757 | 3.3447 | 20.4309 | 139 | 2018-07-24 | 9900333496 | M/s KRIDL | P0190 | Works sanctioned by Hon Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.23776 | Pending
3913 | July | 2018-07-24 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000010 | Construction of RCC drain with covering slab at 1st G Cross balance portion of SBI Staff colony in ward no.74 | Footpaths & Walkability | 000191 | 2016-08-19 | 000408 | 2017-01-30 | 000881 | 2017-01-30 | 17 | 004146 | 2018-07-20 | 14.8376 | 2.073 | 12.7645 | 139 | 2018-07-24 | 9900333496 | KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.14838 | Pending
4342 | August | 2018-08-04 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000032 | Consultancy services for preparation of DPR for the work of Construction of Ambedkar Bhavan 3rd main Kamalanagara in ward no 74 | Other Ward Works | 000078 | 2016-12-19 | 000056 | 2018-07-02 | 000055 | 2018-07-02 | 17 | 004732 | 2018-08-02 | 0.75 | 0.075 | 0.675 | 155 | 2018-08-04 | 9844024123 | M/s V.S Consultants | P3111 | State Finance Commission Untied Grant Works | ddo326 | Executive Engineer SWM 1 Central Zone | 0.0075 | Spill Over
4343 | August | 2018-08-04 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000031 | Consultancy services for preparation of RFP for the work of Construction of Maternity Hospital in ward no 74 | Other Ward Works | 000082 | 2016-12-19 | 000055 | 2018-07-02 | 000054 | 2018-07-02 | 17 | 004733 | 2018-08-02 | 1.5 | 0.15 | 1.35 | 155 | 2018-08-04 | 9844024123 | M/s Nandish Associates | P3111 | State Finance Commission Untied Grant Works | ddo326 | Executive Engineer SWM 1 Central Zone | 0.015 | Spill Over
4472 | August | 2018-08-06 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000011 | Providing cc road at 3rd cross Bhuvaneshwari nagara 6th main 3rd cross Sy.no.46 Kamalanagara in ward no.74 | Roads & Drivablility | 000192 | 2016-08-19 | 000413 | 2017-02-03 | 000882 | 2017-02-04 | 17 | 004627 | 2018-08-01 | 31.1644 | 4.4592 | 26.7052 | 159 | 2018-08-06 | 9900333496 | M/s KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.31164 | Pending
4473 | August | 2018-08-06 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000027 | Construction of RCC drain with covering slab at opposite to Basavanna temple road in ward no 74 Shakthiganapathinagar | Footpaths & Walkability | 000352 | 2016-11-16 | 000401 | 2017-01-27 | 000913 | 2017-02-27 | 17 | 004647 | 2018-08-01 | 17.8056 | 2.4595 | 15.3461 | 159 | 2018-08-06 | 9900333496 | kridl | P2415 | Reserve fund for TandF Committee | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.17806 | Pending
4474 | August | 2018-08-06 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000028 | Construction of RCC drain with covering slab and CC road at 1st cross Kereyangala in ward no 74 Shakthiganapathinagar | Footpaths & Walkability | 000353 | 2016-11-16 | 000402 | 2017-01-27 | 000914 | 2017-02-27 | 17 | 004648 | 2018-08-01 | 11.8886 | 1.6505 | 10.2381 | 159 | 2018-08-06 | 9900333496 | kridl | P2415 | Reserve fund for TandF Committee | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.11889 | Pending
4475 | August | 2018-08-06 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000029 | Construction of RCC drain with covering slab at 2nd cross Kereyangala in ward no 74 Shakthiganapathinagar | Footpaths & Walkability | 000354 | 2016-11-16 | 000403 | 2017-01-16 | 000915 | 2017-02-27 | 17 | 004649 | 2018-08-01 | 19.7586 | 2.6978 | 17.0608 | 159 | 2018-08-06 | 9900333496 | kridl | P2415 | Reserve fund for TandF Committee | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19759 | Pending
5246 | September | 2018-09-03 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000065 | Providing and fixing of LED Street lights in Ward No 74 in Mahalakshmi lyt Division | Footpaths & Walkability | 000066 | 2017-10-28 | 000043 | 2018-07-19 | 000042 | 2018-07-19 | 17 | 005589 | 2018-08-31 | 5.6344 | 0.49906 | 5.1353 | 186 | 2018-09-03 | 9845273024 | Himagiri Sree Electricals | P3110 | 14th Finance Commission Grant Works | ddo209 | Assistant Executive Engineer Electrical West Zone | 0.056344 | Spill Over
5247 | September | 2018-09-03 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000023 | RE-construction of steps and CC for cross roads at Vallbhaganapathi temple in Sy no 46 in Ward no -74 Shankthiganapathinagara | Other Ward Works | 000146 | 2016-06-29 | 000508 | 2017-03-31 | 001067 | 2017-03-31 | 16 | 005469 | 2018-08-28 | 9.3306 | 1.4373 | 7.8932 | 193 | 2018-09-03 | 9900333496 | kridl | P0190 | Works sanctioned by Hon Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.093305 | Pending
5248 | September | 2018-09-03 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000024 | Providing CC road and Improvement to drains in cross roads infront of basavanna temple in Ward no -74 Shankthiganapathinagara | Roads & Drivablility | 000084 | 2016-06-20 | 000507 | 2017-03-30 | 001068 | 2017-03-31 | 16 | 005470 | 2018-08-28 | 9.8492 | 1.4343 | 8.4149 | 193 | 2018-09-03 | 9900333496 | kridl | P0190 | Works sanctioned by Hon Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.098492 | Pending
6093 | October | 2018-10-12 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000079 | Providing additional GYM equipments to kuvempu park in ward NO.74 | Trees, Parks & Playgrounds | 000088 | 2017-06-27 | 000043 | 2017-09-26 | 000070 | 2017-09-27 | 17 | 006181 | 2018-10-04 | 19.9902 | 2.6188 | 17.3713 | 229 | 2018-10-12 | 9900333496 | kridl | P3075 | Special comprehensive development works in Bangalore city (Bangalore city in charge Minister Discretionary Grants) | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.1999 | Pending
6094 | October | 2018-10-12 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000034 | Improvements to drain at 1st 2nd 3rd 4th and 5th cross road of Sy No 46 Kamalanagar in ward no 74 | Footpaths & Walkability | 000356 | 2016-11-18 | 000005 | 2017-04-27 | 000033 | 2017-04-28 | 17 | 006036 | 2018-10-01 | 24.7245 | 3.8735 | 20.851 | 230 | 2018-10-12 | 9900333496 | M/s KRIDL | P0190 | Works sanctioned by Hon Mayor | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.24724 | Pending
6851 | October | 2018-10-25 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000008 | Construction of RCC Drains at 5th cross road Gruhalakshmi layout in Ward No 74 (W0095) | Footpaths & Walkability | 000245 | 2018-02-23 | 000145 | 2018-03-13 | 000245 | 2018-03-14 | 18 | 006906 | 2018-10-22 | 19.9363 | 2.3516 | 17.5848 | 248 | 2018-10-25 | 9900333496 | kridl | P3332 | Special Development works at Ward No. 02,12,22,23,24,25,30,31,37, 38,40,41,42,47,49,53,55,56,59,73,77,78,81,74,87,97,102,117,118,120,121,131,134,136,140,135,147,148,152,157,170,172,176 ( 43 wards Rs.4.00 Cr. Each) | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19936 | Pending
6852 | October | 2018-10-25 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000009 | Construction of RCC Drains at 3rd main road Gruhalakshmi layout in Ward no 74(W0097) | Footpaths & Walkability | 000241 | 2018-02-23 | 000147 | 2018-03-13 | 000246 | 2018-03-14 | 18 | 006907 | 2018-10-22 | 32.9424 | 4.0199 | 28.9226 | 248 | 2018-10-25 | 9900333496 | kridl | P3332 | Special Development works at Ward No. 02,12,22,23,24,25,30,31,37, 38,40,41,42,47,49,53,55,56,59,73,77,78,81,74,87,97,102,117,118,120,121,131,134,136,140,135,147,148,152,157,170,172,176 ( 43 wards Rs.4.00 Cr. Each) | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.32942 | Pending
6991 | October | 2018-10-30 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-16-000003 | Asphalting in Gruhalakshmi Layout (3 cross roads and 3 main roads) in Ward No. 74 | Roads & Drivablility | 000062 | 2016-06-20 | 000071 | 2017-05-19 | 000150 | 2017-05-25 | 16 | 006764 | 2018-10-16 | 15.8322 | 1.2199 | 14.6123 | 255 | 2018-10-30 | 0 | B.B.Umesh | P1771 | Zone Works - POW Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.15832 | Pending
7072 | October | 2018-10-31 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000032 | Consultancy services for preparation of DPR for the work of Construction of Ambedkar Bhavan 3rd main Kamalanagara in ward no 74 | Other Ward Works | 000078 | 2016-12-19 | 000056 | 2018-07-02 | 000055 | 2018-07-02 | 17 | 004732 | 2018-08-02 | 31.1168 | 0.9947 | 30.1221 | 258 | 2018-10-31 | 9449721396 | Narahari .D (M/s Benaka Developers and Projects Pvt Ltd) | P3111 | State Finance Commission Untied Grant Works | ddo326 | Executive Engineer SWM 1 Central Zone | 0.31117 | Spill Over
7073 | October | 2018-10-31 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000031 | Consultancy services for preparation of RFP for the work of Construction of Maternity Hospital in ward no 74 | Other Ward Works | 000082 | 2016-12-19 | 000055 | 2018-07-02 | 000054 | 2018-07-02 | 17 | 004733 | 2018-08-02 | 75.7066 | 2.5969 | 73.1097 | 258 | 2018-10-31 | 9449721396 | Narahari D (M/s Benaka Developers and Projects Pvt Ltd | P3111 | State Finance Commission Untied Grant Works | ddo326 | Executive Engineer SWM 1 Central Zone | 0.75707 | Spill Over
7074 | October | 2018-10-31 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000056 | Additional works to Indira Canteen opposite to BWSSB water tank inWard no-74 Shakthiganapathi nagar. | Indira Canteen | 000041 | 2018-06-11 | 000058 | 2018-06-25 | 000120 | 2018-06-25 | 18 | 007046 | 2018-10-27 | 13.4865 | 1.3573 | 12.1293 | 260 | 2018-10-31 | 9900333496 | kridl | P3106 | Nagarothana Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.13487 | Current
7375 | November | 2018-11-23 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000037 | Desilting of Secondary drains in ward no 74 | Footpaths & Walkability | 000121 | 2018-09-29 | 000194 | 2018-10-23 | 000327 | 2018-10-23 | 18 | 007512 | 2018-11-22 | 9.9952 | 1.0381 | 8.9571 | 272 | 2018-11-23 | 9900333496 | kridl | P3297 | 14th Finance Commission Grants - SWD Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.099952 | Current
7376 | November | 2018-11-23 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000035 | U G D works in ward no 74 | Water & Sanitary | 000137 | 2018-10-11 | 000192 | 2018-10-23 | 000328 | 2018-10-23 | 18 | 007514 | 2018-11-22 | 14.992 | 1.767 | 13.225 | 272 | 2018-11-23 | 9900333496 | kridl | P3295 | 14th Finance Commission Works - UGD Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.14992 | Current
7377 | November | 2018-11-23 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000036 | Maintenance of footpath and roads in ward no 74 | Footpaths & Walkability | 000122 | 2018-09-29 | 000193 | 2018-10-23 | 000329 | 2018-10-23 | 18 | 007515 | 2018-11-22 | 14.9912 | 1.7659 | 13.2253 | 272 | 2018-11-23 | 9900333496 | kridl | P3296 | 14th Finance Commission Works - Road and Footpath Maintenance | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.14991 | Current
7732 | December | 2018-12-14 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000044 | Improvements of Kuvempu park in ward no 74 | Trees, Parks & Playgrounds | 000033 | 2017-02-04 | 000044 | 2017-10-11 | 000058 | 2017-10-11 | 17 | 007760 | 2018-12-10 | 29.9281 | 3.7079 | 26.2202 | 292 | 2018-12-14 | 9845355689 | Executive Engineer, KRIDL | P2178 | Works sanctioned by Dy. Mayor | ddo326 | Executive Engineer SWM 1 Central Zone | 0.29928 | Pending
8007 | December | 2018-12-21 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000060 | Construction of culverts in ward No.74 Shakthiganapathinagara | Footpaths & Walkability | 000453 | 2017-03-04 | 000087 | 2017-05-25 | 000200 | 2017-05-31 | 17 | 007789 | 2018-12-10 | 12.3419 | 0.93403 | 11.4078 | 301 | 2018-12-21 | 9590281209 | J.G.Ravindra (SrilLakshmi venkateshwara enterprises) | P1771 | Zone Works - POW Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.12342 | Pending
8008 | December | 2018-12-21 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000026 | Construction of RCC drain with covering slab at 1st B cross and southern side of Basavanna temple Kereyangnala in ward no 74 Shakthiganapathinagar | Footpaths & Walkability | 000351 | 2016-11-16 | 000040 | 2017-04-28 | 000205 | 2017-05-31 | 17 | 007790 | 2018-12-10 | 19.6848 | 2.8032 | 16.8815 | 301 | 2018-12-21 | 9900333496 | M/s KRIDL | P2415 | Reserve fund for TandF Committee | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.19685 | Pending
8523 | January | 2019-01-10 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000063 | Improvements to Kuvempu park in ward No.74 Shakthiganapathinagara | Trees, Parks & Playgrounds | 000690 | 2017-03-09 | 000068 | 2017-11-30 | 000112 | 2017-12-01 |  | 008147 | 2018-12-21 | 41.691 | 2.0096 | 39.6814 | 320 | 2019-01-10 | 0 | G.Chandrashekar.G | P1771 | Zone Works - POW Works | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.41691 | Pending
8797 | January | 2019-01-25 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000032 | Maintenance of ward office ward no 74 | Other Ward Works | 000195 | 2018-12-22 | 000262 | 2018-12-22 | 000426 | 2018-12-29 |  | 008946 | 2019-01-24 | 4.9955 | 0.50863 | 4.4869 | 333 | 2019-01-25 | 9900333496 | kridl | P3292 | 14th Finance Commission Works - Community Property Maintenance (including Parks) | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.049955 | Current
8802 | January | 2019-01-25 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000034 | Maintenance of Exiting toilet in ward no 74 | Health & Sanitation | 000194 | 2018-12-22 | 000263 | 2018-12-22 | 000427 | 2018-12-29 |  | 008951 | 2019-01-24 | 4.9981 | 0.50202 | 4.496 | 333 | 2019-01-25 | 9900333496 | kridl | P3294 | 14th Finance Commission Works - General Public ToiletandSeptage Maintenance | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.049981 | Current
8803 | January | 2019-01-25 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000031 | Maintenance of BBMP building in ward no 74 | Public Amenities | 000193 | 2018-12-22 | 000261 | 2018-12-22 | 000428 | 2018-12-29 |  | 008952 | 2019-01-24 | 4.9974 | 0.50058 | 4.4968 | 333 | 2019-01-25 | 9900333496 | KRIDL | P3291 | 14th Fin -Maintenance of Cremotorium, Burial Grounds | ddo201 | Assistant Executive Engineer Mahalakshmipuram West Zone | 0.049974 | Current
9815 | March | 2019-03-22 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-18-000030 | Providing and maintenance of Street light in ward no 74 | Footpaths & Walkability | 000059 | 2018-09-14 | 000168 | 2018-12-04 | 000167 | 2018-12-04 |  | 009828 | 2019-03-20 | 9.9455 | 1.2531 | 8.6924 | 382 | 2019-03-22 | 9845008155 | Executive Engineer 4 KRIDL | P3290 | 14th Finance Commission Works - Providing Street Lights and Maintenance | ddo209 | Assistant Executive Engineer Electrical West Zone | 0.099455 | Current
9883 | March | 2019-03-26 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000031 | Consultancy services for preparation of RFP for the work of Construction of Maternity Hospital in ward no 74 | Other Ward Works | 000082 | 2016-12-19 | 000055 | 2018-07-02 | 000054 | 2018-07-02 |  | 004733 | 2018-08-02 | 24.9966 | 1.3598 | 23.6368 | 386 | 2019-03-26 | 9449721396 | Narahari D (M/s Benaka Developers and Projects Pvt Ltd | P3111 | State Finance Commission Untied Grant Works | ddo326 | Executive Engineer SWM 1 Central Zone | 0.24997 | Spill Over
9884 | March | 2019-03-26 | 74 | Shakthi Ganapathi Nagara | Mahalakshmi Layout | Mahalakshmi Layout | West | 074-17-000032 | Consultancy services for preparation of DPR for the work of Construction of Ambedkar Bhavan 3rd main Kamalanagara in ward no 74 | Other Ward Works | 000078 | 2016-12-19 | 000056 | 2018-07-02 | 000055 | 2018-07-02 |  | 004732 | 2018-08-02 | 16.783 | 0.89093 | 15.8921 | 386 | 2019-03-26 | 9449721396 | Narahari .D (M/s Benaka Developers and Projects Pvt Ltd) | P3111 | State Finance Commission Untied Grant Works | ddo326 | Executive Engineer SWM 1 Central Zone | 0.16783 | Spill Over