## Sheet1
SL No | Month | Date | Ward_No | Ward_Name | Job_Code | Job_Description | Work_ Order | Work_Order_Date | Sub Bill Register_No | Sub Bill Register_Date | Bill Register No | Bill Register Date | Job Code Year | CBR_No | CBR_Date | Gross_ Amount In Lakhs | Deduction In Lakhs | Nett_ Amount In Lakhs | RTGS_No | RTGS_Date | Contractor Number | Contractor_Name | P_Code | Budget_Head | Budget_ Head_ID | Engineer Details | Gross_ Amount In Cr
32 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000024 | Preration of detailed of Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-B Block No.45 To 48) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000012 | 2017-04-21 | 000016 | 2017-06-29 | 000020 | 2017-08-26 | 17 | 007280 | 2017-11-02 | 15.0361 | 1.5361 | 13.5 | 1 | 2018-04-04 | 9999999999 | The Technical Manager,(KRIDL), | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.15036
33 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000015 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-A Block No.09 To 12) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000003 | 2017-04-21 | 000007 | 2017-06-29 | 000014 | 2017-08-26 | 17 | 007282 | 2017-11-02 | 36.2039 | 3.7039 | 32.5 | 1 | 2018-04-04 | 8888888888 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.36204
34 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000021 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-C Block No.33 To 36) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000009 | 2017-04-21 | 000013 | 2017-06-29 | 000018 | 2017-08-26 | 17 | 007275 | 2017-11-02 | 8.8253 | 0.86531 | 7.96 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.088253
35 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000013 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-A Block No.01 To 04) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000001 | 2017-04-21 | 000005 | 2017-06-29 |  |  | 17 |  |  | 46.9528 | 4.3906 | 42.5622 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.46953
36 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000019 | Prepartion of Detailed Projest Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-C Block No.25 To 28) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000007 | 2017-04-21 | 000011 | 2017-06-29 | 000026 | 2017-08-29 | 17 | 007276 | 2017-11-02 | 8.8201 | 0.88011 | 7.94 | 1 | 2018-04-04 | 8888888888 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.088201
37 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000017 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-A Block No.17 To 20) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000005 | 2017-04-21 | 000009 | 2017-06-29 | 000005 | 2017-08-24 | 17 | 007277 | 2017-11-02 | 31.2875 | 3.0875 | 28.2 | 1 | 2018-04-04 | 8888888888 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.31287
38 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000016 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-A Block No.13 To 16) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000004 | 2017-04-21 | 000008 | 2017-06-29 | 000006 | 2017-08-24 | 17 | 007278 | 2017-11-02 | 29.8829 | 2.9829 | 26.9 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.29883
39 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000014 | Preparation of Detailed Project Reort for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-A Block No.05 To 08) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000002 | 2017-04-21 | 000006 | 2017-06-29 | 000012 | 2017-08-26 | 17 | 007281 | 2017-11-02 | 21.7719 | 2.0719 | 19.7 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.21772
40 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000026 | Preparation od Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-B Block No.53 To 56) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000014 | 2017-04-21 | 000018 | 2017-06-29 | 000010 | 2017-08-26 | 17 | 007279 | 2017-11-02 | 8.2249 | 0.82495 | 7.4 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL), | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.08225
41 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000023 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-B Block No.41 To 44) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000011 | 2017-04-21 | 000015 | 2017-06-29 | 000015 | 2017-08-26 | 17 | 007274 | 2017-11-02 | 17.3331 | 1.7331 | 15.6 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL), | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.17333
42 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000020 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-C Block No.29 To 32) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000008 | 2017-04-21 | 000012 | 2017-06-30 | 000019 | 2017-08-26 | 17 | 007271 | 2017-11-02 | 8.8077 | 0.82352 | 7.9842 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.088077
43 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000022 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-C Block No.37 To 40) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000010 | 2017-04-21 | 000014 | 2017-06-29 | 000003 | 2017-08-24 | 17 | 007273 | 2017-11-02 | 104.4829 | 9.6829 | 94.8 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL), | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 1.0448
44 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000027 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-B Block No.57 To 58) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000015 | 2017-04-21 | 000019 | 2017-06-29 | 000021 | 2017-08-28 | 17 | 007264 | 2017-11-02 | 4.1008 | 0.42082 | 3.68 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.041008
45 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000025 | Preparation of Detailed Project Report forthe work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-B Block No.49 To 52) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000013 | 2017-04-21 | 000017 | 2017-06-29 | 000013 | 2017-08-26 | 17 | 007272 | 2017-11-02 | 14.603 | 1.403 | 13.2 | 1 | 2018-04-04 | 9999999999 | The technical Manager,(KRIDL), | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.14603
46 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000018 | Preparation of Detailed project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 16 Du.s G 1 Structure) (Type-I-C Block No.21 To 24) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000006 | 2017-04-21 | 000010 | 2017-06-29 | 000011 | 2017-08-26 | 17 | 007270 | 2017-11-02 | 8.8093 | 0.80931 | 8 | 1 | 2018-04-04 | 9999999999 | The Technical Manager (KRIDL) | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.088093
47 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | R-042-16-000004 | Consultancy Services for Preparation of detailed Project Report for the 3 Works in Rajarajeswari Nagara Division | 000056 | 2016-08-29 | 000225 | 2017-01-16 | 000225 | 2017-01-16 | 16 | 003619 | 2017-06-30 | 130.6414 | 5.1414 | 125.5 | 3 | 2018-04-04 | 9902103553 | M/S GANAPATHI STONE CRUSHER | P1732 | Road network arterial roads (Project Division and Major Road Division) | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 1.3064
48 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | 042-17-000004 | Consultancy Services for Preparation of Detailed Project Report For The Work Of Construction and Upgradation of Hospital, school and Bangalore One center in ward no 42,37, 129, and 17 of RR Nagara Constituency | 000097 | 2017-02-07 | 000058 | 2018-03-07 | 000184 | 2018-03-07 | 17 | 000175 | 2018-04-04 | 4.9 | 0.49 | 4.41 | 3 | 2018-04-04 | 9999999999 | Civil Expert Consultants & Testing Centre, | P3106 | Nagarothana Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.049
49 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | R-042-16-000003 | Improvements and asphalting to burial ground road Muneswara temple road and surrounding at Goraguntepalya in Ward No 42 Lakshmidevinagar RR Nagara Zone | 000106 | 2017-04-01 | 000061 | 2018-03-08 | 000193 | 2018-03-08 | 16 | 000176 | 2018-04-04 | 326.7792 | 13.7792 | 313 | 3 | 2018-04-04 | 1234567890 | GANAPATHI STONE CRUSHER | P1733 | Roadwidening Other Roads | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 3.2678
50 | April | 2018-04-04 | 42 | Lakshmi Devi Nagara | R-042-16-000005 | Improvements and asphalting to Goraguntepalya main road silent road Kannika Parameshwari road at Goraguntepalya in Ward No 42 Lakshmidevinagar RR Nagara Zone | 000106 | 2017-03-09 | 000059 | 2018-03-08 | 000191 | 2018-03-08 | 16 | 000177 | 2018-04-04 | 237.3716 | 44.6716 | 192.7 | 3 | 2018-04-04 | 9902103553 | M/S GANAPATHI STONE CRUSHER | P1733 | Roadwidening Other Roads | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 2.3737
242 | April | 2018-04-06 | 42 | Lakshmi Devi Nagara | 042-17-000001 | Consultancy Services for Preparation of Detailed Project Report for the 1 Works in Rajarajeswari Nagara Division | 000059 | 2016-09-26 | 000224 | 2017-01-16 | 000224 | 2017-01-16 | 17 | 000987 | 2017-04-28 | 6.3812 | 0.63815 | 5.7431 | 7 | 2018-04-06 | 9986551818 | Civil Expert Consultants & Testing Center, | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.063812
243 | April | 2018-04-06 | 42 | Lakshmi Devi Nagara | 042-16-000021 | Comperansive Development of Roads and Drains in ward no 38 and 42Package-02 | 000070 | 2016-10-25 | 000026 | 2017-01-18 | 000251 | 2017-03-18 | 16 | 000389 | 2017-04-18 | 4.9 | 0.49 | 4.41 | 7 | 2018-04-06 | 9986551818 | Civil Experts Consultants & Testing Center, | P3106 | Nagarothana Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.049
510 | April | 2018-04-13 | 42 | Lakshmi Devi Nagara | 042-17-000004 | Consultancy Services for Preparation of Detailed Project Report For The Work Of Construction and Upgradation of Hospital, school and Bangalore One center in ward no 42,37, 129, and 17 of RR Nagara Constituency | 000097 | 2017-02-07 | 000058 | 2018-03-07 | 000184 | 2018-03-07 | 17 | 000175 | 2018-04-04 | 154.2188 | 4.7808 | 149.4381 | 17 | 2018-04-13 | 9845543771 | P Gopalkrishna | P3106 | Nagarothana Works | ddo008 | Executive Engineer (Project) Rajarajeshwari Nagar Zone | 1.5422
650 | April | 2018-04-25 | 42 | Lakshmi Devi Nagara | 042-17-000009 | Providing and fixing of LED Street lights in Ward No 42 in RR Nagar Division | 000064 | 2018-03-14 | 000125 | 2018-03-28 | 000125 | 2018-03-28 | 17 | 000607 | 2018-04-19 | 10.3827 | 0.21804 | 10.1647 | 24 | 2018-04-25 | 9845044408 | Shankar Rao B, Prop. Sri Manjunatha Enterprises | P3110 | 14th Finance Commission Grant Works | ddo009 | Executive Engineer (Electrical) Rajarajeshwari Nagar Zone | 0.10383
699 | April | 2018-04-26 | 42 | Lakshmi Devi Nagara | 042-18-000003 | Consultancy Services for Preparation of Detailed Project Report for the Works of SC/ST Welfare grant total 6 works in Ward no.42. | 000059 | 2018-01-19 | 000064 | 2018-03-31 | 000021 | 2018-04-23 | 18 |  | 2018-06-20 | 96.9757 | 8.9757 | 88 | 25 | 2018-04-26 | 9611354208 | The Technical Manager | P1878 | 18per - Works (Bhagyajyothi, Sooru / Neeru Yojane and General) (54 Lakhs / New Wards) | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.96976
943 | May | 2018-05-09 | 42 | Lakshmi Devi Nagara | 042-17-000029 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 12 Du.s G 2 Structure) (Type-III 1 Individual and 3 Composite - Block No.08, 09, 10, 11, 12, 20 and 21) In Vambay Quarters, Laggere Sy.No.9-2, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000017 | 2017-04-21 | 000021 | 2017-06-29 | 000023 | 2017-08-28 | 17 | 007285 | 2017-11-02 | 190.3527 | 18.7905 | 171.5622 | 47 | 2018-05-09 | 9999999999 | The Technical Manager (KRIDL), | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 1.9035
1618 | June | 2018-06-01 | 42 | Lakshmi Devi Nagara | 042-16-000015 | Providing and fixing water supply pipeline in missing line in Lakshmidevinagara in ward no 42 | 000042 | 2016-06-30 | 000019 | 2016-12-30 | 000212 | 2016-12-30 | 16 | 001973 | 2018-05-26 | 5.2485 | 0.6585 | 4.59 | 64 | 2018-06-01 | 9900027228 | Raghavendra B | P1802 | Water Supply New Areas | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.052485
2815 | July | 2018-07-02 | 42 | Lakshmi Devi Nagara | 042-16-000014 | Supplying of Water through water tanker in Lakshmidevinagara in ward no 42 | 000043 | 2016-06-30 | 000020 | 2016-12-30 | 000214 | 2016-12-30 | 16 | 003191 | 2018-06-29 | 7.9089 | 1.2148 | 6.6942 | 107 | 2018-07-02 | 9999999999 | Sri, Raghavendra B | P1802 | Water Supply New Areas | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.079089
2987 | July | 2018-07-03 | 42 | Lakshmi Devi Nagara | 042-18-000007 | Providing UGD Works and Comprehensive development works in Jaibhuvaneshwari Nagar Havadigara Colony at Ward No 42 Lakshmidevi Nagara | 000103 | 2018-03-08 | 000015 | 2018-06-06 | 000027 | 2018-06-06 | 18 | 002817 | 2018-06-20 | 92.0802 | 10.1452 | 81.935 | 110 | 2018-07-03 | 9611354208 | The Technical Manager | P1878 | 18per - Works (Bhagyajyothi, Sooru / Neeru Yojane and General) (54 Lakhs / New Wards) | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.9208
3147 | July | 2018-07-09 | 42 | Lakshmi Devi Nagara | 042-16-000005 | Construction of Hallow block drain with Kerb stone with covering slab at 6th cross 3rd block Nandhini Layout Lakshmidevinagara in ward no 42 | 000048 | 2016-06-30 | 000017 | 2016-12-30 | 000209 | 2016-12-30 | 16 | 003428 | 2018-07-07 | 18.1752 | 2.2252 | 15.95 | 117 | 2018-07-09 | 9141433220 | Sri, Gangadharaswamy, | P1771 | Zone Works - POW Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.18175
3148 | July | 2018-07-09 | 42 | Lakshmi Devi Nagara | 042-16-000006 | Construction of Hallow block drain with covering slab and kerb at 4th cross Kaverinagara Lakshmidevinagara in ward no 42 | 000049 | 2016-06-30 | 000018 | 2016-12-30 | 000208 | 2016-12-30 | 16 | 003429 | 2018-07-07 | 19.2078 | 2.3577 | 16.85 | 117 | 2018-07-09 | 9141433220 | Sri, Gangadharaswamy, | P1771 | Zone Works - POW Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.19208
3149 | July | 2018-07-09 | 42 | Lakshmi Devi Nagara | 042-16-000008 | Improvements to C C Road and construction of RCC drain at 1st Main 5th cross Back side of Chowdeshwari Temple Nandhini Layout Lakshmidevinagara in ward no 42 | 000040 | 2016-06-30 | 000023 | 2016-12-30 | 000211 | 2016-12-30 | 16 | 003430 | 2018-07-07 | 20.9396 | 2.5966 | 18.343 | 117 | 2018-07-09 | 9611414936 | CN Shivanna | P1771 | Zone Works - POW Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.2094
3240 | July | 2018-07-12 | 42 | Lakshmi Devi Nagara | 042-17-000006 | Improvements and development of Goraguntepalya crematorium and other allied works in ward no 42 | 000003 | 2017-09-14 | 000021 | 2018-07-02 | 000044 | 2018-07-02 | 17 | 003574 | 2018-07-11 | 28.004 | 1.704 | 26.3 | 122 | 2018-07-12 | 9743746317 | M/s RR Infratech | P3111 | State Finance Commission Untied Grant Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.28004
3372 | July | 2018-07-17 | 42 | Lakshmi Devi Nagara | 042-18-000007 | Providing UGD Works and Comprehensive development works in Jaibhuvaneshwari Nagar Havadigara Colony at Ward No 42 Lakshmidevi Nagara | 000103 | 2018-03-08 | 000015 | 2018-06-06 | 000027 | 2018-06-06 | 18 | 002817 | 2018-06-20 | 4.495 | 0.4495 | 4.0455 | 126 | 2018-07-17 | 9886998316 | M/s.Civil Quality Consultants & Engineers | P1878 | 18per - Works (Bhagyajyothi, Sooru / Neeru Yojane and General) (54 Lakhs / New Wards) | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.04495
3469 | July | 2018-07-18 | 42 | Lakshmi Devi Nagara | 042-16-000003 | Operation and Maintenance of Street Light System in Ward No. 42-Lakshmidevinagar(P-Nandini lay out) Package R10 of RajarajeshwariNagar Zone. | 000036 | 2017-02-28 | 000088 | 2018-01-18 | 000088 | 2018-01-18 | 16 | 003762 | 2018-07-13 | 4.7209 | 0.32398 | 4.3969 | 127 | 2018-07-18 | 9448886499 | M/S GS Electricals Prop.S Manjunath, | P0300 | M and R to Street Lights - Replacement of Burnt Bulbs etc. (Package) | ddo009 | Executive Engineer (Electrical) Rajarajeshwari Nagar Zone | 0.047209
3902 | July | 2018-07-24 | 42 | Lakshmi Devi Nagara | 042-16-000010 | Pot hole fillings in Lakshmidevinagara in ward no 42 | 000046 | 2018-04-01 | 000021 | 2016-12-30 | 000210 | 2016-12-30 | 16 | 004079 | 2018-07-20 | 11.4713 | 1.5913 | 9.88 | 139 | 2018-07-24 | 9999999999 | Sri, Ragavendra B, | P1771 | Zone Works - POW Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.11471
3903 | July | 2018-07-24 | 42 | Lakshmi Devi Nagara | 042-16-000011 | Maintanance of silt and Tractor in Lakshmidevinagara in ward no 42 | 000044 | 2018-04-01 | 000022 | 2016-12-30 | 000213 | 2016-12-30 | 16 | 004080 | 2018-07-20 | 7.2245 | 1.0701 | 6.1543 | 139 | 2018-07-24 | 9999999999 | Sri, Raghavendra, B | P1771 | Zone Works - POW Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.072245
4083 | July | 2018-07-27 | 42 | Lakshmi Devi Nagara | 042-17-000006 | Improvements and development of Goraguntepalya crematorium and other allied works in ward no 42 | 000003 | 2017-09-14 | 000021 | 2018-07-02 | 000044 | 2018-07-02 | 17 | 003574 | 2018-07-11 | 2.52 | 0.252 | 2.268 | 145 | 2018-07-27 | 9742959595 | M/s.Civil Experts Consultants and Testing center | P3111 | State Finance Commission Untied Grant Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.0252
4420 | August | 2018-08-06 | 42 | Lakshmi Devi Nagara | 042-16-000002 | Operation and Maintenance of Street Light System in Ward No. 42-Lakshmidevinagar(P-Goragontepalya ) Package R9 of RajarajeshwariNagar Zone. | 000004 | 2017-04-28 | 000087 | 2018-01-18 | 000087 | 2018-01-18 | 16 | 004815 | 2018-08-03 | 3.6702 | 0.23788 | 3.4323 | 157 | 2018-08-06 | 9448886499 | M/s GS Electricals Prop. S Manjunath, | P0300 | M and R to Street Lights - Replacement of Burnt Bulbs etc. (Package) | ddo009 | Executive Engineer (Electrical) Rajarajeshwari Nagar Zone | 0.036702
5084 | August | 2018-08-25 | 42 | Lakshmi Devi Nagara | 042-16-000004 | Operation and Maintenance of Street Light System in Ward No. 42-Lakshmidevinagar(P-Lakshmidevinagar) Package R11 of RajarajeshwariNagar Zone. | 000037 | 2017-02-28 | 000086 | 2018-01-18 | 000086 | 2018-01-18 | 16 | 005305 | 2018-08-21 | 5.173 | 0.33355 | 4.8394 | 180 | 2018-08-25 | 9448886499 | M/S GS Electricals Prop.S Manjunath, | P0300 | M and R to Street Lights - Replacement of Burnt Bulbs etc. (Package) | ddo009 | Executive Engineer (Electrical) Rajarajeshwari Nagar Zone | 0.05173
5085 | August | 2018-08-25 | 42 | Lakshmi Devi Nagara | 042-18-000003 | Consultancy Services for Preparation of Detailed Project Report for the Works of SC/ST Welfare grant total 6 works in Ward no.42. | 000059 | 2018-01-19 | 000064 | 2018-03-31 | 000021 | 2018-04-23 | 18 | 005226 | 2018-08-14 | 8.4016 | 0.8402 | 7.5614 | 181 | 2018-08-25 | 9448064921 | ACS Design Consulting Pvt Ltd | P1878 | 18per - Works (Bhagyajyothi, Sooru / Neeru Yojane and General) (54 Lakhs / New Wards) | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.084016
5830 | October | 2018-10-06 | 42 | Lakshmi Devi Nagara | 042-17-000006 | Improvements and development of Goraguntepalya crematorium and other allied works in ward no 42 | 000003 | 2017-09-14 | 000016 | 2017-11-14 | 000062 | 2017-11-14 | 17 | 007959 | 2017-11-18 | 23.1638 | 1.4638 | 21.7 | 221 | 2018-10-06 | 9743746317 | M/s RR Infratech | P3111 | State Finance Commission Untied Grant Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.23164
5831 | October | 2018-10-06 | 42 | Lakshmi Devi Nagara | 042-17-000006 | Improvements and development of Goraguntepalya crematorium and other allied works in ward no 42 | 000003 | 2017-09-14 | 000016 | 2017-11-14 | 000062 | 2017-11-14 | 17 | 007959 | 2017-11-18 | 23.1638 | 1.4638 | 21.7 | 221 | 2018-10-06 | 9743746317 | M/s RR Infratech | P3111 | State Finance Commission Untied Grant Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.23164
5993 | October | 2018-10-12 | 42 | Lakshmi Devi Nagara | 042-17-000001 | Consultancy Services for Preparation of Detailed Project Report for the 1 Works in Rajarajeswari Nagara Division | 000059 | 2016-09-26 | 000224 | 2017-01-16 | 000224 | 2017-01-16 | 17 | 000987 | 2017-04-28 | 603.674 | 31.674 | 572 | 232 | 2018-10-12 | 8884312499 | Sri, Uday Shivakumar, | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 6.0367
5994 | October | 2018-10-12 | 42 | Lakshmi Devi Nagara | 042-16-000021 | Comperansive Development of Roads and Drains in ward no 38 and 42Package-02 | 000070 | 2016-10-25 | 000023 | 2018-07-27 | 000075 | 2018-07-30 | 16 | 006360 | 2018-10-07 | 1.5782 | 0.0647 | 1.5135 | 232 | 2018-10-12 | 8884312499 | Ishwar naik | P3106 | Nagarothana Works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 0.015782
5995 | October | 2018-10-12 | 42 | Lakshmi Devi Nagara | 042-17-000028 | Preparation of Detaild Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 12 Du.s G 1 Structure) (Type-II Block No.59 To 63) In Jaibhuvaneshwarinagara, Laggere Sy.No.11and 12, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000016 | 2017-04-21 | 000020 | 2017-06-29 | 000016 | 2017-08-26 | 17 | 007265 | 2017-11-02 | 155.3617 | 14.5263 | 140.8353 | 233 | 2018-10-12 | 9999999999 | The Technical Manager (KRIDL), | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 1.5536
5996 | October | 2018-10-12 | 42 | Lakshmi Devi Nagara | 042-17-000031 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 12 Du.s G 2 Structure) (Type-III 3 Individual and 2 Composite - Block No.01, 02, 03, 04, 05, 06 and 07) In Vambay Quarters, Laggere Sy.No.9-2, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000019 | 2017-04-21 | 000023 | 2017-06-29 | 000022 | 2017-08-28 | 17 | 007283 | 2017-11-02 | 180.7118 | 16.8966 | 163.8152 | 233 | 2018-10-12 | 9999999999 | The Technical Manager (KRIDL), | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 1.8071
5997 | October | 2018-10-12 | 42 | Lakshmi Devi Nagara | 042-17-000030 | Preparation of Detailed Project Report for the work of Providing Special Repairs and Restoration Works To Old Dilapilated Houses (Each Block 12 Du.s G 2 Structure) (Type-III 1 Individual and 3 Composite - Block No.13, 14, 15, 16, 17, 18 and 19) In Vambay Quarters, Laggere Sy.No.9-2, Lakshmidevinagara In Rajarajeshwarinagara Constituency. | 000018 | 2017-04-21 | 000022 | 2017-06-29 | 000024 | 2017-08-28 | 17 | 007284 | 2017-11-02 | 190.3518 | 18.3517 | 172 | 233 | 2018-10-12 | 9999999999 | The Technical Manager (KRIDL), | P3158 | SIP Infrastructure Project works | ddo477 | Assistant Executive Engineer Goruguntapalya Sub Division Rajarajeshwari Nagar Zone | 1.9035
5998 | October | 2018-10-12 | 42 | Lakshmi Devi Nagara | 042-16-000017 | Consultancy Services for Preparation of Detailed project Report for the Work of Construction of Bridge to storm water Drain and Improvements to Approach Rad at 2nd cross 1st Stage Nandhini Layout (Near SRS School) in ward no 42 Under Package-09 | 000007 | 2016-04-15 | 000005 | 2017-05-25 | 000021 | 2017-05-26 | 16 | 003491 | 2017-06-27 | 106.0022 | 3.6926 | 102.3096 | 233 | 2018-10-12 | 9844185764 | N.M Krishnamurthy | P3089 | Special Development works in 7 CMC and 1 TMC area in BBMP | ddo008 | Executive Engineer (Project) Rajarajeshwari Nagar Zone | 1.06
6924 | October | 2018-10-29 | 42 | Lakshmi Devi Nagara | 042-16-000017 | Consultancy Services for Preparation of Detailed project Report for the Work of Construction of Bridge to storm water Drain and Improvements to Approach Rad at 2nd cross 1st Stage Nandhini Layout (Near SRS School) in ward no 42 Under Package-09 | 000007 | 2016-04-15 | 000005 | 2017-05-25 | 000021 | 2017-05-26 | 16 | 003491 | 2017-06-27 | 1.89 | 0.189 | 1.701 | 252 | 2018-10-29 | 828606202 | Tejus Consultant | P3089 | Special Development works in 7 CMC and 1 TMC area in BBMP | ddo008 | Executive Engineer (Project) Rajarajeshwari Nagar Zone | 0.0189